## 2014 Work Plan
Milestone Keys:
2014 Project Work Plan (Status Updated: 1/26/2014)
IC- Initial Comment |  | This worksheet is an estimate of anticipated milestones for projects in 2014, and it is intended to be a project management tool for use in tracking status of projects under development compared to those anticipated milestones. Detailed information for each project is available from the project pages on the NERC website. Projects that remain from 2013's Project Tracking Spreadsheet that were not prioritized in the RSDP, but that are continuing beyond the first quarter of 2014, are also represented here. Projects that are not anticipated to continue beyondb Note that projects listed here represent known projects for 2014. As facts and circumstances warrant, it may be necessary to update this tool as 2014 progresses, and additional projects may be added in response to regulatory directives, input from RISC, or to meet goals of the NERC strategic plan.
IB- Initial Ballot
AB - Additional Ballot
PB- Presented to BOT
F-Projected filing with FERC
FYRP- Five-year Review Posting
FYRR - Five-year Review Recommendation to SC
Project Status
No Issues with Project
Project Off Schedule by One Quarter
Project Off Schedule by Two or more Quarters |  | Projected Posting Schedule
No Development Work in Progress |  | The above is a link to the schedule of upcoming postings, which is updated weekly. It includes near term posting projections.
[13 empty] | JAN | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP | OCT |  | NOV | DEC |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Project Number | Activity/Project (Project Names Hyperlinked to Project Page) | Deliverable | Deadline, if any | Priority in 2014-2016 RSDP, if applicable (see Note 1, below) | 2013 P81 Reqs | # of Directives | # of Guidances | Comments | PMOS Liaison | NERC Contact | Status: Green, Yellow, Red | Milestones: Planned vs. Actual/Projected | First Quarter |  |  |  |  | Second Quarter | [5 empty] | Third Quarter |  |  |  |  | Fourth Quarter |  |  |  |  | First Quarter |  |  | Second Quater |  |  | Third Quarter |  |  | Fourth Quarter
2009-03 | Emergency Operations | EOP-001, EOP-002, EOP-003 |  | High | 14 | 3 | 2 |  | Gary Kruempel | Laura Anderson |  | Plan |  | IB | [11 empty] | PB |  |  | F
[7 empty] | 2 |  |  |  |  | Actual/Projected |  | IB | [7 empty] | IB | [12 empty] | PB | F
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | New Standards |  | High |  | 2 |  | Continuing to develop consensus on scope, working with PMOS member to develop plan. | Jennifer Sterling | Ed Dobrowolski |  | Plan | [8 empty] | IB | [5 empty] | AB |  |  |  | PB |  |  | F
[7 empty] | 0 |  |  |  |  | Actual/Projected | [8 empty] | IB | [5 empty] | AB |  |  |  | PB |  |  | F
2010-02 | Connecting new facilities to the grid/Five-year Review of FAC standards | FAC-001, FAC-002 |  | Low |  | 1 | 1 | SC accepted FYR recommendation. Work to be scheduled in 2014. | Ken Goldsmith | Mallory Huggins |  | Plan |  | PB |  |  |  |  | IB | [6 empty] | PB |  |  | F
[7 empty] | 1 |  |  |  |  | Actual/Projected |  | PB |  |  |  |  | IB | [6 empty] | PB |  |  | F
2010-14.2 | Phase 2 of Balancing Authority Reliability-based Control; Time Error, AGC, and Inadvertent | BAL-004, BAL-005-0.1b, BAL-006-2 |  | Medium | 11 | 7 | 6 | Developer assigned, work in progress. | Ken Goldsmith | Sean Cavote |  | Plan | FYRR | PB |  |  |  |  | IB | [6 empty] | PB |  |  | F
[7 empty] | 6 |  |  |  |  | Actual/Projected |  | FYRP |  |  |  | FYRR |  | PB |  |  |  | IB | [5 empty] | PB |  |  | F
2010-03 | Demand Data (MOD C) | MOD-016, MOD-017, MOD-018, MOD-019, MOD-020, MOD-021 |  | N/A | 10 | 10 | 4 | The project received a 57.59% approval on its second ballot. The SDT is meeting on 12/5/13 to review industry comments. | Scott Miller | Darrel Richardson |  | Plan
[7 empty] | 4 |  |  |  |  | Actual/Projected | [7 empty] | PB |  |  |  | F
2013-04 | VAR Directives | VAR-002 |  | N/A | 3 | 6 | 5 | VAR-001, which addresses the FERC directives, passed the 45-day ballot. VAR-002 received a 66.16% approval rating. The SDT is meeting to review industry comments. | Ron Parsons | Soo Jin Kim |  | Plan
[7 empty] | 5 |  |  |  |  | Actual/Projected |  |  | AB |  |  |  |  | PB |  |  |  | F
2007-06 | System Protection Coordination | PRC-001, PRC-027 |  | N/A |  | 1 |  | Due to a misunderstanding with Project 2010-01, incorrect information was posted for comment in September. The posting was pulled to correct the information and will be reposted soon. | Jennifer Sterling | Al McMeekin |  | Plan |  | PB
[7 empty] | 0 |  |  |  |  | Actual/Projected |  | AB | [5 empty] | PB
2007-11 | Disturbance Monitoring | PRC-002, PRC-018 |  | Medium | 2 |  | 1 |  | Guy Zito | Steve Crutchfield |  | Plan | [11 empty] | F
[7 empty] | 1 |  |  |  |  | Actual/Projected | [7 empty] | PB |  |  |  | F
2010-05.1 | Phase 1 of Protection Systems: Misoperations | PRC-003, PRC-004 |  | N/A |  |  | 2 | The SDT is considering comments from the last posting and modifications to PRC-004. The SDT met with RAPA and SC members in September to discuss options. | Jennifer Sterling | Scott Barfield |  | Plan
[7 empty] | 2 |  |  |  |  | Actual/Projected | AB | [6 empty] | PB
2008-02 | Undervoltage Load Shedding | PRC-010, PRC-022 |  | High | 2 | 1 | 1 |  | Jennifer Sterling | Erika Chanzes |  | Plan |  | IB | [11 empty] | PB |  |  | F
[7 empty] | 1 |  |  |  | Delayed to coordinate with the development of the SPS definition | Actual/Projected |  | IB | [7 empty] | IB | [12 empty] | PB | F
2010-14.1 | BARC Directives and Issues-Project 2010-14.1 Balancing Authority Reliability-based Controls | BAL-001, BAL-002, BAL-013 |  | N/A | 4 |  |  | Will go to BOT in February due to industry concerns on BAL-002 | Ron Parsons | Darrel Richardson |  | Plan
[7 empty] | 0 |  |  |  |  | Actual/Projected |  | AB | [5 empty] | PB |  |  |  | F
2013-03 | Geomagnetic Disturbance Mitigation Stage II | New Standards | FERC filing deadline of January 21, 2015 | High |  | 14 |  |  | Brian Murphy | Mark Olson |  | Plan | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB | F
[12 empty] | Actual/Projected | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB | F
2010-05.2 | Special Protection Systems: Phase 2 of Protection Systems | PRC | Self-imposed deadline for definition of SPS is February 2015 for coordination with other PRC projects. | Medium |  |  |  | Additional BOT mtg added. First is for definition of SPS; the second is for the standards. | Matt Morais | Al McMeekin |  | Plan | [9 empty] | IB | [12 empty] | PB | F
[12 empty] | Actual/Projected | [9 empty] | IB | [12 empty] | PB | F | [7 empty] | PB
2012-09 | Implementation of IRO Review Recommendations | IRO-003, IRO-004, IRO-008, IRO-009, IRO-010 |  | Medium | 2 | 2 |  |  | Brian Murphy | Soo Jin Kim |  | Plan | [15 empty] | IB | [6 empty] | PB |  | F
[12 empty] | Actual/Projected | [15 empty] | IB | [6 empty] | PB |  | F
2012-13 | Implementation of NUC Review Recommendations | NUC-001 |  | Low |  |  |  |  | PMOS Oversight | Stephen Eldridge |  | Plan | [6 empty] | IB | [6 empty] | PB |  |  | F
[12 empty] | Actual/Projected | [6 empty] | IB | [6 empty] | PB |  |  | F
2007-17.3 | Protection System Maintenance: Sudden Pressure Relays | PRC-005-4 |  | Pending Technical Committee Input (See comments) | 1 | 1 |  | The technical committee provided a report, but the project has not yet been evaluated for prioritization. | Charles Yeung | Jordan Mallory |  | Plan | [15 empty] | IB | [6 empty] | PB |  | F
[12 empty] | Actual/Projected | [15 empty] | IB | [6 empty] | PB |  | F
2010-13.3 | Relay Loadability Stable Power Swings | PRC |  | Pending Technical Committee Input (See comments) |  |  |  | The technical committee provided a report, but the project has not yet been evaluated for prioritization. | Charles Long | Scott Barfield |  | Plan |  |  |  |  | IB | [5 empty] | AB | [7 empty] | PB | F
|  |  | FERC filing deadline of December 31, 2014 | [8 empty] | Actual/Projected |  |  |  |  | IB | [5 empty] | AB | [7 empty] | PB | F
TBD | TOP/IRO Revisions | TOP/IRO | Pending FERC action on NERC motion, deadline of January 31, 2015 | Pending Prioritization in 1Q 2014 |  |  |  |  | Brian Murphy | Ed Dobrowolski |  | Plan | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB |  |  | F
[12 empty] | Actual/Projected | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB |  |  | F
2014-02 | CIP Version 5 Revisions | CIP | FERC filing deadline for certain directives of February 3, 2015. | Pending Prioritization in 1Q 2014 |  | 8 |  |  | Brian Murphy | Marisa Hecht and Ryan Stewart |  | Plan | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB |  |  | F
[12 empty] | Actual/Projected | [7 empty] | IB |  |  |  |  | AB | [5 empty] | PB |  |  | F
TBD | TPL Directive | TPL-001-4 | Goal is to complete directives and file in time for FERC action prior to implementing TPL-001-4 | Pending Prioritization in 1Q 2014 |  | 1 |  |  | Matt Morais | Ed Dobrowolski |  | Plan |  |  |  | IB |  |  |  | PB |  |  |  | F
[12 empty] | Actual/Projected |  |  |  | IB |  |  |  | PB |  |  |  | F
TBD | Standards Applicability for Dispersed Generation Resources | Various | Goal is to complete prior to BES Phase 2 implementation 7/1/2016 | Pending Prioritization in 1Q 2014 |  |  |  |  | Gary Kruempel | Sean Cavote |  | Plan | [15 empty] | IB | [6 empty] | PB |  | F
[12 empty] | Actual/Projected | [15 empty] | IB | [6 empty] | PB |  | F
Note 1: The prioritizations here reflect those prioritizations assigned as part of the 2014-2016 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2014, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2014 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2014." As discussed in the 2014-2016 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee.