## 2015 Work Plan
Milestone Keys:
Project Tracking Spreadsheet: 2015 Project Work Plan (Status Updated: 3/3/2015)
SP- SAR Posting |  | This worksheet displays estimates of anticipated standards development milestones for projects in 2015, and it is intended to be a project management tool for use in tracking the status of projects under development compared to their anticipated milestones. Detailed information for each project is available from their respective project pages on the NERC website. Projects that remained from 2014's Project Tracking Spreadsheet that were not prioritized in the RSDP, but that are continuing beyond the first quarter of 2015, are also represented here. Projects not anticipated to continue beyond the first quarter of 2015 are not included (information for those projects remains available under the "Standards Under Development" page on the NERC website). Note that projects listed here represent known projects for 2015. As facts and circumstances warrant, it may be necessary to update this tool, and additional projects may be added in response to regulatory directives, input from RISC, or to meet goals of the NERC strategic plan.
IB- Initial Ballot
AB - Additional Ballot
PB- Presented to BOT
F-Projected filing with FERC
PRP- Periodic Review Posting
PRR - Periodic Review Recommendation to SC
Project Status
No Issues with Project
Project Off Schedule by One Quarter
Project Off Schedule by Two or more Quarters |  | Projected Posting Schedule
No Development Work in Progress |  | The above is a link to the schedule of upcoming postings, which is updated weekly. It includes near term posting projections.
[14 empty] | 2015 | [21 empty] | 2016
[14 empty] | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT | NOV |  | DEC | JAN | FEB | MAR |  | APR | MAY | JUN | JUL | AUG |  | SEP | OCT | NOV | DEC
Project Number | Activity/Project (Project Names Hyperlinked to Project Page) | Deliverable | Deadline, if any | Priority in 2015-2017 RSDP, if applicable (see Note 1, below) | 2013 P81 Reqs | Number of Directives | # of Guidances (see Note 2) | Directionally consistent with IERP findings | Comments | PMOS Liaison | NERC Contact | Status: Green, Yellow, Red | Milestones: Planned vs. Actual/Projected (See Notes 3 and 4) | First Quarter | [5 empty] | Second Quarter | [5 empty] | Third Quarter | [5 empty] | Fourth Quarter |  |  |  | First Quarter |  |  |  | Second Quarter |  |  | Third Quarter |  |  |  | Fourth Quarter
2007-06 | System Protection Coordination | PRC-027 |  | N/A |  |  |  |  | The SPCSDT is continuing work on draft 5 of PRC-027-1. The SDT expects the standard to be posted for formal comment and ballot in April. | Jennifer Sterling | Al McMeekin |  | 2015 PMOS Plan |  |  |  | AB | [5 empty] | AB |  |  |  |  | PB |  |  |  | F
[7 empty] | 0 |  |  |  |  | Project extended to address an additional issue by FERC | Actual/Projected | [6 empty] | AB | [5 empty] | AB | [6 empty] | PB |  |  | F
2007-06.2 | Phase 2: System Protection Coordination | PRC-001-1.1., PRC-028 | NERC-imposed deadline of 12/31/2015 | N/A |  |  |  |  | Originally PRC-001-1.1. | Brenda Hampton | Scott Barfield |  | 2015 PMOS Plan | [9 empty] | IB |  |  |  |  | AB |  |  |  |  | PB |  |  | QQA2
[7 empty] | 1 | [5 empty] | Actual/Projected | [9 empty] | IB |  |  |  |  | AB |  |  |  |  | PB |  |  | F
2008-02.2 | Undervoltage Load Shedding for PRC-004 | PRC-004 and PRC-010 |  | N/A |  |  |  |  | A 45-day additional comment period and ballot are open until April 7. | Jennifer Sterling | Scott Barfield |  | 2015 PMOS Plan |  |  |  | IB |  |  |  |  | PB |  |  |  | F
[7 empty] | 1 | [5 empty] | Actual/Projected |  |  |  | IB |  |  |  |  | PB |  |  |  | F
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | New standard |  | N/A |  | 3 |  |  | Nominations close Friday, March 6. | Jennifer Sterling | Mark Olson | Phased to start after TOP/IRO Project 2014-03 completion | 2015 PMOS Plan | [7 empty] | SP |  |  |  | IB |  |  |  | AB |  |  |  | AB |  |  |  | PB |  |  | F
[7 empty] | 0 | [5 empty] | Actual/Projected | [10 empty] | SP |  |  |  |  | IB |  |  |  | AB |  |  |  | PB |  |  | F
2010-05.3 | Phase 3 of Protection System Misoperations: RAS | Revised Definition of Remedial Action Scheme |  | N/A |  |  |  |  | Project 2010-05.2 Phase 2 of Protection Systems was separated into two phases. In Phase 1, the SPSSDT developed a revised definition for the term Remedial Action Scheme (RAS) which was adopted by the NERC BOT in November 2014. Phase 2 will address the six SPS/RAS-related Reliability Standards. The standards will be consolidated and will address all aspects of SPS/RAS. The SDT began standards development in January and has meetings scheduled for February, March, and April. | Colt Norrish | Al McMeekin |  | 2015 PMOS Plan | [6 empty] | IB | [5 empty] | AB |  |  |  |  | AB | [5 empty] | PB |  |  | F
[7 empty] | 2 | [5 empty] | Actual/Projected | [9 empty] | IB | [5 empty] | AB |  |  |  |  | AB |  |  | PB |  |  | F
2010-14.1.2 | Phase 1 of Balancing Authority Reliability-based Controls: Reserves | BAL-002 |  | N/A |  |  |  |  | A 45-day additional comment period and ballot are open until March 16. | Ron Parsons | Darrel Richardson |  | 2015 PMOS Plan |  |  | AB | [5 empty] | PB |  |  |  | F
[7 empty] | 1 | [5 empty] | Actual/Projected |  |  | AB | [5 empty] | PB |  |  |  | F
2010-14.2.1 | BAL-005 and BAL-006 | BAL-005 and BAL-006 |  | N/A | 11 | 7 |  |  | The SDT anticipates posting the first draft of the revised standards for industry comment in mid-April 2015. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  |  | IB | [5 empty] | PB |  |  |  | F
[7 empty] | 1 | [5 empty] | Actual/Projected | [7 empty] | IB | [5 empty] | AB | [5 empty] | PB |  |  | F
2010-14.2.2 | Periodic Review of BAL-004 | BAL-004 |  | N/A |  |  |  |  | A 45-day additional ballot comment period and ballot are open until March 16. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  | PRP |  |  |  |  | PRP
[7 empty] | 4 | [5 empty] | Actual/Projected | [5 empty] | SP |  |  |  |  | IB |  |  |  | PB
2015-06 | IRO Review | IRO-006-East, IRO-009 |  | N/A | 2 | 2 |  |  | Submitting SAR for authorization to post at March SC meeting. | TBD | TBD |  | 2015 PMOS Plan | [5 empty] | PRP |  |  |  | PRP |  |  |  |  | PRR
[7 empty] | 2 | [5 empty] | Actual/Projected | [5 empty] | SP |  |  |  | IB |  |  |  |  | AB |  |  |  |  | PB
2014-01 | Dispersed Generation Resources | PRC-005 |  | N/A |  |  |  |  | PRC-005-5 posted for final ballot until March 11. | Jennifer Sterling | Katherine Street |  | 2015 PMOS Plan | IB | [7 empty] | PB |  |  |  | F
[13 empty] | Actual/Projected | IB | [7 empty] | PB |  |  |  | F
2014-04 | Physical Security Directives | CIP-014 |  | N/A |  | 1 |  |  | The drafting team met January 27th and made revisions to the standard to address the directive. The team will ask for SC authorization to post for a 45-day comment/initial ballot on February 18. We are still on target for May BOT meeting. | Brian Murphy | Steve Crutchfield |  | 2015 PMOS Plan |  |  | IB | [5 empty] | PB |  |  |  | F
|  |  | FERC filing deadline of December 31, 2014 | [9 empty] | Actual/Projected |  |  |  | IB |  |  |  |  | PB |  |  |  | F
2015-01 | TPL Directive | TPL-001 |  | Medium (prioritized by SC in 2014) |  |  |  |  | This project has been put on hold indefinitely due to data collecting requirements. | Ron Parsons | Steve Crutchfield |  | 2015 PMOS Plan | [22 empty] | SP |  |  | IB |  |  | AB |  |  | AB |  |  | PB
[7 empty] | 0 | [5 empty] | Actual/Projected | [22 empty] | SP |  |  | IB |  |  | AB |  |  | AB |  |  | PB
2015-02 | Emergency Operations Periodic Review | EOP-004, EOP-005, EOP-006, and EOP-008 |  | Medium |  |  |  |  | Team was appointed by SC on Feb. 3 and project is in development. | Ken Goldsmith | Laura Anderson |  | 2015 PMOS Plan | [5 empty] | PRP |  |  |  | PRP |  |  |  | PRR
[7 empty] | 6 | [5 empty] | Actual/Projected | [5 empty] | PRP |  |  |  | PRP |  |  |  | PRR
2015-03 | Periodic Review of System Operating Limit Standards | FAC-010, FAC-011, and FAC-014 |  | Medium |  |  |  |  | Team was appointed by SC on Feb. 3 and project is in development. | Brian Murphy | Mark Olson |  | 2015 PMOS Plan | [7 empty] | PRP | [5 empty] | PRP |  |  |  |  | PRR
[13 empty] | Actual/Projected | [8 empty] | PRP |  |  |  |  | PRP |  |  |  |  | PRR
2015-04 | Alignment of NERC Glossary of Terms and Definitions Used in the Rules of Procedure | Glossary Terms |  | Low |  |  |  |  | Team was appointed by SC on Feb. 3 and project is in development. | Andrew Gallo | Lacey Ourso |  | 2015 PMOS Plan |  |  |  |  | SP |  |  |  |  | IB |  |  |  | AB | [5 empty] | PB |  |  | F
[13 empty] | Actual/Projected |  |  |  |  | SP |  |  |  |  | IB |  |  |  | AB | [5 empty] | PB |  |  | F
2007-17.4 | PRC-005 Order No. 803 Directive | PRC-005 | [6 empty] | The Standards Committee will be asked to authorize a posting for additional drafting team members at its March 11, 2015 meeting. |  | Steve Crutchfield |  | 2015 PMOS Plan | [5 empty] | SP |  |  |  | IB |  |  |  |  | AB |  |  |  |  | PB |  |  | F
[13 empty] | Actual/Projected | [5 empty] | SP |  |  |  | IB |  |  |  |  | AB |  |  |  |  | PB |  |  | F
2010-04.1 | MOD-031 Order No. 804 Directives | MOD-031 | [8 empty] | Darrel Richardson |  | 2015 PMOS Plan | [7 empty] | SP |  |  | IB |  |  |  |  | PB
[13 empty] | Actual/Projected | [7 empty] | SP |  |  | IB |  |  |  |  | PB
2010-INT-03 | Interpretation for TOP-002-2a R2, R8, and R19 for FMPP | TOP-002-2a | [8 empty] | TBD |  | 2015 PMOS Plan
Actual/Projected
2012-INT-07 | Interpretation for CIP-005 for AEP | CIP-005 | [8 empty] | TBD |  | 2015 PMOS Plan
Actual/Projected
Note 1: The prioritizations here reflect those prioritizations assigned as part of the 2015-2017 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2015, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2015 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2015." As discussed in the 2015-2017 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee.
Note 2: Refers to guidances from regulatory orders for standards activity to consider, but that do not carry the same effect as a directive.
Note 3: In the columns at right, in some cases, an "additional ballot" is not indicated for planning purposes, but if consensus is not supported on an initial ballot, or if substantive changes occur, one will be scheduled.
Note 4: In the columns at right, there are no "plan" milestones in some cases because the project was originally planned to be complete in 2014, and the project's "actual" milestones have extended into 2015).
Note 5: In the column labeled "directionally consistent with IERP findings," directionally consistent indicates whether the Standard Drafting Team, when the project is completed, considered the recommendations from the Independent Expert Review Project and the Paragraph 81 project. After the Standard Drafting Team has considered the recommendations, the materials posted with the standards will describe the Standard Drafting Team's consideration of the findings.

## Sheet3
IB | PB | F