## 2015-2016 Work Plan
Milestone Keys:
Project Tracking Spreadsheet: 2016 Project Work Plan (Status Updated: TBD)
SP- SAR Posting | SP - SAR Posting | This worksheet displays estimates of anticipated standards development milestones for projects in 2016, and it is intended to be a project management tool for use in tracking the status of projects under development compared to their anticipated milestones. Detailed information for each project is available from their respective project pages on the NERC website. Projects that remained from 2015's Project Tracking Spreadsheet that were not prioritized in the RSDP, but that are continuing beyond the first quarter of 2016, are also represented here. Projects not anticipated to continue beyond the first quarter of 2016 are not included (information for those projects remains available under the "Standards Under Development" page on the NERC website). Note that projects listed here represent known projects for 2016. As facts and circumstances warrant, it may be necessary to update this tool, and additional projects may be added in response to regulatory directives, input from RISC, or to meet goals of the NERC strategic plan.
IB- Initial Ballot | IC - Initial Ballot
AB - Additional Ballot | AB - Additional Ballot
PB- Presented to BOT | PB - Presented to BOT
F-Projected filing with FERC | F - Projected Filing with FERC
PRP- Periodic Review Posting | PRP - Periodoc Review Posting
PRR - Periodic Review Recommendation to SC
Project Status
No Issues with Project
Project Off Schedule by One Quarter
Project Off Schedule by Two or more Quarters |  | Projected Posting Schedule
No Development Work in Progress |  | The above is a link to the schedule of upcoming postings, which is updated weekly. It includes near term posting projections.
[14 empty] | 2015 | [22 empty] | 2016
[14 empty] | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | JAN |  | FEB |  | MAR |  | APR |  | MAY | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV | DEC
Project Number | Activity/Project (Project Names Hyperlinked to Project Page) | Deliverable | Deadline, if any | Priority in 2015-2017 RSDP, if applicable (see Note 1, below) | 2013 P81 Reqs | Number of Directives | # of Guidances (see Note 2) | Directionally consistent with IERP findings | Comments | PMOS Liaison | NERC Contact | Status: Green, Yellow, Red | Milestones: Planned vs. Actual/Projected (See Notes 3 and 4) | First Quarter | [5 empty] | Second Quarter | [5 empty] | Third Quarter | [5 empty] | Fourth Quarter |  |  |  |  | First Quarter | [5 empty] | Second Quarter |  |  |  |  | Third Quarter | [5 empty] | Fourth Quarter
2007-06 | System Protection Coordination | PRC-027 | NERC-imposed deadline of 12/31/2015 | N/A |  |  |  |  | Additional ballot closed November 14, 2015 and passed at 80.94%. | Brenda Hampton | Al McMeekin |  | 2015 PMOS Plan |  |  |  | AB | [5 empty] | AB |  |  |  |  | PB |  |  |  | F
[7 empty] | 1 | [5 empty] | Actual/Projected | [6 empty] | AB | [6 empty] | AB | [6 empty] | AB |  | PB | F | [8 empty] | F
2007-06.2 | Phase 2: System Protection Coordination | PRC-001-1.1.(ret.), TOP-009-1 | NERC-imposed deadline of 12/31/2015 | N/A |  |  |  |  | Did not pass November 2015 ballot and the team is reviewing next steps. | Brenda Hampton | Scott Barfield |  | 2015 PMOS Plan | [9 empty] | IB |  |  |  |  | AB | [5 empty] | PB |  |  | QQA2
[7 empty] | 1 | [5 empty] | Actual/Projected | [14 empty] | IB |  |  |  |  | AB |  |  |  |  | AB | [6 empty] | PB | F
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | TOP-010, IRO-018 |  | N/A |  | 3 |  |  | IRO-018-1 and TOP-010-1 posted for comment and initial ballot September 24 - November 9, 2015. Additional posting December 9, 2015 - January 22, 2016. The standards received passing weighted segment approval. The SDT will meet Feb 2-4 to review comments, revise, and determine next steps. | Jennifer Sterling | Mark Olson |  | 2015 PMOS Plan | [7 empty] | SP |  |  |  | IB |  |  |  | AB |  |  |  |  | AB |  |  |  |  | PB |  |  |  | F
[7 empty] | 0 | [5 empty] | Actual/Projected | [13 empty] | SP |  |  |  | IB |  |  |  |  | AB |  |  |  | AB |  |  |  |  | PB |  |  | F
2010-05.3 | Phase 3 of Protection System Misoperations: RAS | Revised Definition of Remedial Action Scheme |  | N/A |  |  |  |  | Project 2010-05.2 Phase 2 of Protection Systems was separated into two phases. In Phase 1, the SPSSDT developed a revised definition for the term Remedial Action Scheme (RAS) which was adopted by the NERC BOT in November 2014. Phase 2 will address the six SPS/RAS-related Reliability Standards. The standards will be consolidated and will address all aspects of SPS/RAS. The SDT began standards development in January and has meetings scheduled for February, March, April, and July. | Colt Norrish | Al McMeekin |  | 2015 PMOS Plan | [6 empty] | IB | [5 empty] | AB |  |  |  |  | AB | [7 empty] | PB |  |  |  | F
[7 empty] | 2 | [5 empty] | Actual/Projected | [8 empty] | Informal | [6 empty] | IB | [6 empty] | AB |  |  | AB | [5 empty] | PB | F
2010-14.2.1 | BAL-005 and BAL-006 | BAL-005 | N/A | 11 | 7 |  |  |  | Additional ballot November 10, 2015 to January 11, 2016. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  |  | IB | [5 empty] | PB |  |  |  | F | [8 empty] | PB
[7 empty] | 1 | [5 empty] | Actual/Projected | [14 empty] | IB | [7 empty] | AB |  |  | PB |  | F
2010-14.2.1 | BAL-005 and BAL-006 | FAC-001 | N/A | 11 | 7 |  |  |  | Additional ballot November 10, 2015 to January 11, 2016. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  |  | IB | [5 empty] | PB |  |  |  | F | [8 empty] | PB
[7 empty] | 1 | [5 empty] | Actual/Projected | [14 empty] | IB | [7 empty] | AB |  |  | PB |  | F
2010-14.2.1 | BAL-005 and BAL-006 | BAL-006 | N/A | 11 | 7 |  |  |  | Additional ballot November 10, 2015 to January 11, 2016. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  |  | IB | [5 empty] | PB |  |  |  | F | [8 empty] | PB
[7 empty] | 1 | [5 empty] | Actual/Projected | [14 empty] | IB | [7 empty] | AB |  |  | PB |  | F
2010-14.2.2 | BAL-004 | BAL-004 |  | N/A |  |  |  |  | Final ballot ends December 17, 2015. | Ken Goldsmith | Darrel Richardson |  | 2015 PMOS Plan |  | PRP |  |  |  |  | PRP
[7 empty] | 4 | [5 empty] | Actual/Projected | [5 empty] | SP | [11 empty] | IB | [7 empty] | PB |  | F
2015-01 | TPL Directive (Single Points of Failure) | TPL-001 |  | Medium (prioritized by SC in 2014) |  |  |  |  | This project will address two directives and consider other improvements to TPL‐001‐4 — Transmission System Planning Performance Requirements. There are no remaining timesensitive directives. | Ron Parsons | Steve Crutchfield |  | 2015 PMOS Plan | [23 empty] | SP |  |  |  |  | IB |  |  |  | AB |  |  |  |  | AB |  |  |  |  | PB
[7 empty] | 0 | [5 empty] | Actual/Projected | [23 empty] | SP |  |  |  |  | IB |  |  |  | AB |  |  |  |  | AB |  |  |  |  | PB
2015-07 | COM-001 Order No. 808 Directive | COM-001-3 |  | N/A |  | 1 |  |  | Draft COM-001-3 posted for comments and initial ballot. Ballot period concluded November 16, 2015 and did not pass. Team meet first week of December to consider comments. Outreach to be conducted. | Brenda Hampton | Sean Bodkin and Jordan Mallory |  | 2015 PMOS Plan | [10 empty] | SP |  |  | IB |  |  |  |  | AB |  |  |  |  | AB | [7 empty] | PB |  | F
[13 empty] | Actual/Projected | [10 empty] | SP | [8 empty] | IB | [7 empty] | AB | [8 empty] | PB |  |  |  | F
2015-08 | Emergency Operations | EOP-004, EOP-005, EOP-006, and EOP-008 |  | N/A |  | 1 |  |  | Planning to post for an initial comment period and ballot in mid January 2016. | Ken Goldsmith | Laura Anderson |  | 2015 PMOS Plan | [13 empty] | SP | [10 empty] | IB | [5 empty] | AB | [5 empty] | PB
[13 empty] | Actual/Projected | [13 empty] | SP | [10 empty] | IB | [5 empty] | AB | [5 empty] | PB
2010-07.1 | Vegetation Management | FAC-003 |  | N/A |  |  |  |  | Draft FAC-003-4 posted for comments and initial ballot. Ballot period concluded 12/16/2015. SDT meeting TBD early January 2016 to address comments. | Andrew Gallo | Jordan Mallory/Sean Bodkin |  | 2015 PMOS Plan | [18 empty] | IB | [6 empty] | PB |  |  | F
[13 empty] | Actual/Projected | [18 empty] | IB | [6 empty] | AB | [5 empty] | PB |  | F
2014-02 | CIP Version 5 Revisions | CIP Standards |  | N/A |  |  |  |  | NOPR issued. Pending Final Rule. | Brian Murphy | Steve Crutchfield |  | 2015 PMOS Plan
Actual/Projected
2013-03 | Geomagnetic Disturbance Mitigation | TPL-007-1 | [6 empty] | NOPR issued May 14, 2015. Pending Final Rule. FERC Technical Conference scheduled for March 1, 2016. | Jennifer Sterling | Mark Olson |  | 2015 PMOS Plan
Actual/Projected
2014-03 | Modification to TOP and IRO Standards | TOP and IRO standards | [6 empty] | NOPR issued June 18, 2015. Final Rule issued November 19, 2015 with three directives with an associated 18 month regulatory filing deadline. | Brian Murphy | Mark Olson |  | 2016 PMOS Plan | [27 empty] | SP | [7 empty] | IB | [5 empty] | AB
[13 empty] | Actual/Projected | [24 empty] | SP | [10 empty] | IB | [5 empty] | AB
2015-09 | Establish and Communicate System Operating Limits | FAC-010, FAC-011, and FAC-014 |  | N/A |  |  |  |  | Team appointed Sept 23. Project stems from periodic review. Team met end of November to discuss next steps and revisions. | Andrew Gallo | Lacey Ourso |  | 2015 PMOS Plan | [15 empty] | SP | [14 empty] | IB |  |  |  |  | AB | [5 empty] | AB
[13 empty] | Actual/Projected | [15 empty] | SP | [14 empty] | IB |  |  |  |  | AB | [5 empty] | AB
2015-10 | Single Points of Failure TPL-001 | TPL-001 |  | N/A |  |  |  |  | SAR Drafting Team appointment authorization request--planned for Jan 2016 SC. Project stems from FERC Order No. 754 report (SPCS/SAMS) | TBD | Katherine Street |  | 2016 PMOS Plan | [21 empty] | SP | [8 empty] | IB | [8 empty] | AB |  |  |  |  | AB
[13 empty] | Actual/Projected | [21 empty] | SP | [8 empty] | IB | [8 empty] | AB |  |  |  |  | AB
2015-INT-01 | Interpretation of CIP-002-5.1 for Energy Sector Security Consortium (EnergySec) | CIP-002-5.1 |  | N/A |  |  |  |  | RFI accepted by the SC on September 23, 2015. Next steps are still being determined. | TBD | Lacey Ourso |  | 2016 PMOS Plan | [21 empty] | SP | [8 empty] | IB | [8 empty] | AB |  |  |  |  | AB
Actual/Projected
2015-INT-02 | Interpretation of CIP-007-5 for Foxguard Solutions | CIP-007-5 |  | N/A |  |  |  |  | RFI accepted by the SC on September 23, 2015. Next steps are still being determined. | TBD | Sean Bodkin |  | 2016 PMOS Plan
Actual/Projected
2015-INT-03 | Interpretation of TOP-002-2.1b for FMPP | TOP-002-2.1b |  | N/A |  |  |  |  | RFI accepted by the SC on September 23, 2015. Next steps are still being determined. | TBD | Sean Bodkin |  | 2016 PMOS Plan
Actual/Projected
Note 1: The prioritizations here reflect those prioritizations assigned as part of the 2015-2017 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2015, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2015 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2015." As discussed in the 2015-2017 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee.
Note 2: Refers to guidances from regulatory orders for standards activity to consider, but that do not carry the same effect as a directive.
Note 3: In the columns at right, in some cases, an "additional ballot" is not indicated for planning purposes, but if consensus is not supported on an initial ballot, or if substantive changes occur, one will be scheduled.
Note 4: In the columns at right, there are no "plan" milestones in some cases because the project was originally planned to be complete in 2014, and the project's "actual" milestones have extended into 2015).
Note 5: In the column labeled "directionally consistent with IERP findings," directionally consistent indicates whether the Standard Drafting Team, when the project is completed, considered the recommendations from the Independent Expert Review Project and the Paragraph 81 project. After the Standard Drafting Team has considered the recommendations, the materials posted with the standards will describe the Standard Drafting Team's consideration of the findings.

## Delayed Project Details
Project Number | Activity/Project (Project Names Hyperlinked to Project Page) | Deliverable | PMOS Liaison | NERC Contact | Additional Information regarding delay of project
2007-06.2 | Phase 2: System Protection Coordination | PRC-001-1.1., TOP-009-1 | Brenda Hampton | Scott Barfield | Did not pass Septmber 2015 ballot and will plan to conduct another SDT meeting and post for additional ballot. Goal to post week of Oct. 5, 2015.
2010-14.1 | Phase 1 of Balancing Authority Reliability based Controls: Reserves | BAL-002 | Ron Parsons | Darrel Richardson | Project extended to address an additional issues by FERC.
2010-14.2.1 | BAL-005 and BAL-006 | BAL-005 and BAL-006 | Ken Goldsmith | Darrel Richardson | Difficulty in scheduling SDT meetings.