## 2013-2014 Summary Chart
Standards Development Plan Milestones
IO- Informal Outreach
IC- Initial Comment
IB- Initial Ballot
SB - Successive Ballot
PB- Presented to BOT | [9 empty] | 2013 | [15 empty] | 2014 (Colors are for clarity ONLY)
F-Filed with FERC | [9 empty] | JAN | FEB |  | MAR |  | APR |  | MAY |  | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Activity/Project | Deliverable | 2013 P81 Reqs | # of Directives | # of Guidances |  | Green, Yellow, Red | Comments | PMOS Liaison | NERC Contact | First Quarter |  |  |  |  | Second Quarter |  |  |  |  | Third Quarter |  |  | Fourth Quarter |  |  | First Quarter |  |  | Second Quater |  |  | Third Quarter |  |  | Fourth Quarter
Directives Projects
MOD A-ATC/TTC/CBM-Project 2012-05 ATC Revisions Order 729 | MOD-001, MOD-004, MOD-028, MOD-029, MOD-030 | 48 | 17 |  | Plan |  |  | Scott Miller | Ryan Stewart | [5 empty] | IO |  |  |  |  | IC & IB |  |  |  | PB
|  |  |  | 3 | Actual/Projected | [5 empty] | IO |  |  |  | IO |  |  |  |  | IC & IB |  |  |  | PB
Project 2007-12 Frequency Response | BAL-003 |  | 2 |  | Plan |  |  | N/A | Darrel Richardson |  | PB | [5 empty] | F
|  |  |  | 0 | Actual/Projected | [5 empty] | PB |  | F
BARC Directives and Issues-Project 2010-14.1 Balancing Authority Reliability-based Controls | BAL-012 |  | 4 |  | Plan |  | This standard will not go forward | N/A | Darrel Richardson | IB | [6 empty] | PB & F
[5 empty] | Actual/Projected |  |  |  |  | IB
BARC Directives and Issues-Project 2010-14.1 Balancing Authority Reliability-based Controls | BAL-001, BAL-002, BAL-013 | 4 |  |  | Plan |  | Will go to BOT in Nov rather than Aug; no hurdles | Ken Goldsmith | Darrel Richardson | IB | [11 empty] | PB & F
|  |  |  | 0 | Actual/Projected | [8 empty] | IB | [9 empty] | PB & F
MOD B- Project 2010-03 Modeling Data | MOD-010, MOD-011, MOD-012, MOD-013, MOD-014, MOD-015 | 2 | 16 |  | Plan |  |  | Scott Miller | Steve Noess | IO | [8 empty] | IC & IB |  |  |  |  | PB
|  |  |  | 1 | Actual/Projected |  |  |  |  | IO | IO | [8 empty] | IC & IB |  |  |  | PB
MOD C-Project 2010-04 Demand Data | MOD-016, MOD-017, MOD-018, MOD-019, MOD-020, MOD-021 | 11 | 10 |  | Plan |  |  | Scott Miller | Darrel Richardson |  |  |  | IO | [6 empty] | IC & IB |  |  |  | PB
|  |  |  | 4 | Actual/Projected | [7 empty] | IO | [6 empty] | IC & IB |  |  |  | PB
PER Directives-Project 2010-01 Support Personnel Training | PER-002, PER-005 |  | 4 |  | Plan |  |  | Scott Miller | Jordan Mallory | [5 empty] | IO |  |  |  |  | IC & IB |  |  |  | PB
|  |  |  | 3 | Actual/Projected | [5 empty] | IO |  |  |  | IO |  |  |  |  | IC & IB |  |  |  | PB
NERC Glossary-Project 2012-08 Definitions - phase I (3 definitions) | Add statutory definitions of Bulk Power System, Reliable Operation, and Reliability Standard to NERC Glossary |  | 3 |  | Plan |  |  | Jennifer Sterling | Soo Jin Kim | [5 empty] | IO |  |  |  |  | IC & IB |  |  |  | PB
|  |  |  | 0 | Actual/Projected | [5 empty] | IO |  | IC & IB |  |  |  | PB
NERC Glossary-Project 2012-08 Definitions - phase 2 | Modify existing definition of Transmission Operator and Generator Operator |  | 2 | 0 | Plan |  |  | Jennifer Sterling | Soo Jin Kim |  | IO | [10 empty] | PB
[5 empty] | Actual/Projected | [5 empty] | IO | [10 empty] | PB
VAR Directives- Project 2008-01 | VAR-001, VAR-002 | 3 | 6 | 5 | Plan |  |  | Brian Murphy | Soo Jin Kim |  | IO | [8 empty] | IC & IB |  |  |  | PB
[5 empty] | Actual/Projected | [5 empty] | IO | [8 empty] | IC & IB |  |  |  | PB
Five-Year Review Projects
Project 2007-09 Generator Verification | MOD-024, MOD-025, MOD-026, MOD-027, PRC-019, PRC-024 |  | 4 |  | Plan |  |  | N/A | Steve Crutchfield |  | PB
|  |  |  | 2 | Actual/Projected | [5 empty] | PB | [5 empty] | PB
Project 2008-12 Coordinate Interchange Standards | INT-001-3, INT-003-3, INT-004-2, INT-005-3 INT-006-3, INT-007-1, INT-008-3, INT-009-1, INT-010-1 | 13 | 2 |  | Plan |  |  | Charles Yeung | Steve Crutchfield | IO and SAR Revised |  |  |  |  | IB | [8 empty] | PB
|  |  |  | 8 | Actual/Projected |  |  |  |  | IO and SAR Revised |  |  |  |  | IB | [8 empty] | PB
Project 2009-03 Emergency Operations | EOP-001-2b, EOP-002-3, EOP-003-1, EOP-004-2 (P81, RBS), EOP-005-2 (P81, RBS), EOP-006-2 (RBS), EOP-008-1 (RBS), EOP-009-1, IRO-001-5 | 20 | 3 |  | Plan |  | Cold weather SAR | Gary Kruempel | Laura Anderson | IO & IC |  |  |  |  | IB | [11 empty] | PB
|  |  |  | 1 | Actual/Projected | [5 empty] | IO | [8 empty] | IB | [6 empty] | PB
Project 2009-02 Real-time Reliability Monitoring and Analysis Capabilities | New Standards |  | 2 |  | Plan |  |  | Jennifer Sterling | Ed Dobrowolski | [5 empty] | IO and review/respond to white paper |  |  |  |  | IB | [6 empty] | PB
|  |  |  | 0 | Actual/Projected | [7 empty] | IO and review/respond to white paper | [6 empty] | IC/IB | [6 empty] | PB
Project 2010-11 TPL Footnote 'b" | TPL-001, TPL-002, TPL-003, TPL-004 | 4 | 2 |  | Plan |  |  | N/A | Ed Dobrowolski |  | PB
[5 empty] | Actual/Projected | [5 empty] | PB
Project 2010-17 Definition of Bulk Electric System | Revise Definition of Bulk Electric System |  | 5 |  | Plan |  |  | Jennifer Sterling | Ed Dobrowolski | IB | [16 empty] | PB
|  |  |  | 0 | Actual/Projected | [10 empty] | IB | [10 empty] | PB
Project 2012-09 IRO Review | Various IRO standards | 14 | 0 |  | Plan |  |  | Ron Parson | Steve Crutchfield | IO | [9 empty] | IB | [6 empty] | PB
|  |  |  | 0 | Actual/Projected | [6 empty] | IO | [10 empty] | IB
Project 2012-13 NUC Review | NUC-001 |  | 0 |  | Plan |  |  | Brian Murphy | Sean Cavote | [10 empty] | IO | [11 empty] | IB |  |  |  | PB
|  |  |  | 0 | Actual/Projected | [7 empty] | IO
Project 2010-02 Connecting new facilities to the grid |  |  | 1 |  | Plan |  |  | Ken Goldsmith | Mallory Huggins | IO & SAR Revised |  |  |  |  | IB | [8 empty] | PB
|  |  |  | 1 | Actual/Projected | [7 empty] | IO & Five-year rview | [9 empty] | IB |  |  |  | PB
Projects and Emerging Issues Projects
Project 2007-02 Operating Personnel Communication Protocols | COM-003 |  | 2 |  | Plan |  | yellow due to concern from PMOS members | Brian Murphy | Joe Krisiak | [7 empty] | PB |  | F
|  |  |  | 1 | Actual/Projected | [9 empty] | SB |  | PB |  | F
Project 2007-06 System Protection Coordination | PRC-001, PRC-027 |  | 1 |  | Plan |  |  | Jennifer Sterling | Al McMeekin/ Scott Barfield | [11 empty] | PB |  | F
|  |  |  | 0 | Actual/Projected | [15 empty] | PB |  | F
Project 2007-11 Disturbance Monitoring | PRC-002, PRC-018 | 2 | 0 |  | Plan |  |  | Gary Kruempel | Barb Nutter | [8 empty] | IC & IB | [5 empty] | PB |  | F
|  |  |  | 1 | Actual/Projected | [12 empty] | IC & IB | [5 empty] | PB |  | F
Project 2007-17.2 Protection System Maintenance and Testing | PRC-005 | 1 | 1 |  | Plan |  |  | Gary Kruempel | Al McMeekin |  |  |  |  | IC & IB | [6 empty] | PB |  | F
|  |  |  | 0 | Actual/Projected | [9 empty] | IC & IB | [5 empty] | PB |  | F
Project 2010-05.1 Phase 1 of Protection Systems: Misoperations | PRC-003, PRC-004 |  | 0 |  | Plan |  |  | Jennifer Sterling | Al McMeekin | [11 empty] | PB |  |  | F
|  |  |  | 2 | Actual/Projected | [11 empty] | SB |  |  |  | PB |  |  | F
Project 2010-13.2 Generator Relay Loadability | PRC-025 |  | 0 |  | Plan |  | Initial ballot was 55% | Gary Kruempel | Scott Barfield | IC & IB | [10 empty] | PB |  |  | F
|  |  |  | 1 | Actual/Projected |  |  |  |  | IC & IB | [5 empty] | SB |  |  |  |  | PB |  |  | F
Project 2013-01 Cold Weather Preparedness | New Standards |  | 0 |  | Plan |  |  | Brian Murphy | Barb Nutter | [10 empty] | IC & IB |  |  |  | PB
|  |  |  | 0 | Actual/Projected | [14 empty] | IC & IB |  |  |  | PB
Project 2008-02 Undervoltage Load Shedding | PRC-010, PRC-022 | 3 | 1 |  | Plan |  |  | Jennifer Sterling | Erika Chanzes | [12 empty] | IC |  | IB |  |  | PB
|  |  |  | 1 | Actual/Projected | [16 empty] | IC |  | IB |  |  | PB
Project 2010-14.2 Phase 2 of Balancing Authority Reliability-based Control; Time Error, AGC, and Inadvertent | BAL-004, BAL-005-0.1b, BAL-006-2 | 11 | 7 |  | Plan |  | Coordinator to be assigned depending on pending SB | Ron Parson | TBD | [10 empty] | IO |  |  | IC & IB
|  |  |  | 6 | Actual/Projected | [14 empty] | IO |  |  | IC & IB
| Totals | 136 | 95 | 40 | 2013 Quarterly totals for Para 81 candidates
| P81 Projects dealt with in retirements (e.g. CIP V3, V4 replaced with V5): See P81 tab | 20 |  |  | Yearly totals for Para 81 candidates
| Total | 156 | 135
Note on M32: husseyl: All but PRC-024
Note on S32: husseyl: PRC-024
Note on G35: husseyl: Initiating as a 5-year review rather than as drafting project to address interdependency with Cold Weather and GMD projects
Note on G41: husseyl: Behind one quarter because delivery of final PC report was planned for December but slipped to March. Also awaiting FERC action on requests for rehearing.
Note on G47: husseyl: Intiating as 5-year review project to incorporate input from Standards Review Project.