## owssvr (1)
Task Name | Description | Task Type | Due Date | Subcommittee | Task Status | Priority | Status for Reporting Comments | % Complete | Risk Registry:Risk Category | Risk Registry | Subcommittee:Focus | RSTC Strategic Risk Priorities
C5-SPIDERWG Terminology: Working Definitions Document | Review of existing definitions and terminology and development and coordination of new terms, for consistent reference across sub-groups. | Analysis |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Initial draft complete; will update RSTC as necessary. Subsequent revisions will be explored by team, as needed. Updated with FERC definition of DER. Unlikely will there be a reason to update. | 100% | N/A | N/A | ​Risk Mitigation
C7-Tracking and Reporting DER Growth | Coordinated review of information regarding DER growth, including types of DER, size of DER, etc. Consideration for useful tracking techniques for modeling and reliability studies. | Analysis |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Presentation at August SPIDERWG meeting. Determining best next steps at RSTC. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
O1-White Paper: BPS Perspectives on DER Aggregators | White paper identifying key BPS reliability perspectives with the recently released FERC Order 2222. Being developed by SPIDERG sub-group leadership and Dan Kopin, and will get full review and input from overall SPIDERWG once initial draft complete. | White Paper |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | Focus of early 2022 for SPIDERWG to get to RSTC | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
6-Seasonal Assessment Improvements | Assist RAS with incorporation of probabilistic metrics in the RAS seasonal reports | Assessment |  | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Completed /introduced in 2021 seasonal assessments | 100% | N/A | N/A | ​Reliability and Security Assessment
Information protection | Evaluate the processes and procedures used by entities to share certain types of data (e.g., modeling, load-flow, one-lines) and make recommendations as necessary to improve protection mechanisms. | Collaboration |  | Security Working Group (SWG) | In Progress | (2) Normal | Ongoing; tasks are assigned as needs are identified | 50% | Bulk Power System Planning | Data and Information Requirements | ​Risk Mitigation
Guidance for high priority risks | identify the need for industry guidance to address high priority risks | Guidance |  | Security Working Group (SWG) | In Progress | (2) Normal | Ongoing; tasks are assigned as needs are identified | 50% | N/A | N/A | ​Risk Mitigation
CIP Evidence Request Tool (ERT) - Tools to support internal controls initiatives | Ongoing task to support industry users by providing tools and resources for addressing security controls and relevant compliance outcomes. | Documentation |  | Security Working Group (SWG) | In Progress | (2) Normal | Ongoing activity; specific tasks may be assigned as topics and needs are identified | 50% | Cyber Vulnerabilities | Cyber Security | ​Risk Mitigation
Utility Essential Security Practices Whitepaper | Develop guidance that addresses security protections for utility technologies that are not subject to compliance with the CIP Reliability Standards. Examples of those technologies include inverters, synchro-phasers, natural gas SCADA, etc. (Resources aligned with Electric-Gas Working Group (EGWG) ) | White Paper |  | Security Working Group (SWG) | In Progress | (2) Normal | Task will be addressed as personnel become available; expectation is to collaborate with members from other RSTC groups, such as SITES, Operating Reliability Subcommittee (ORS), and/or Electric-Gas Working Group (EGWG). | 25% | Cyber Vulnerabilities | Non-CIP Protections | ​Risk Mitigation
Preparing for attacks on midstream or interstate natural gas pipelines | Guidance that helps entities prepare for situations that could delay or prevent the delivery and availability of natural gas from suppliers | Study |  | Security Working Group (SWG) | Not Started | (2) Normal | Activity will begin when higher priority projects are complete or when personnel are available to address this task. This effort is likely to include collaboration with other RSTC technical groups as well as E-ISAC | 0% | Resource Adequacy and Performance | Energy Assurance | ​Risk Mitigation
Planning to Reduce the number of Critical Facilities | Collaborate with SITES and other relevant groups to develop approaches to planning, models and simulations that will reduce the number of facilities that meet the criteria to be considered critical to reliability. | Collaboration |  | Security Working Group (SWG) | In Progress | (2) Normal | Task will be addressed as volunteers become available; collaboration is likely with other RSTC groups and E-ISAC | 15% | Cyber Vulnerabilities | Cyber - Other | ​Risk Mitigation
Response to GridEx lessons learned | Placeholder for possible work items stemming from the biennial GridEx lessons learned | Follow Up |  | Security Working Group (SWG) | Not Started | (2) Normal | Placeholder for possible tasks emerging from Grid Exercise (GridEx) VI | 0% | N/A | N/A | ​Risk Mitigation
Create or Update guideline, "Control System Electronic Connectivity" | Review the 2013 guideline and determine whether it should be maintained, revised, or withdrawn or develop Communication Protection System Guideline From WP slides (8-2023) Description: Work Plan item name: Communication Protection System Guideline Work Plan item detailed description: Develop Security Guideline for protection of communications to and between assets containing low impact BES Cyber Systems across publicly accessible networks Scheduled completion date: Q2 2024 Applicability to address (chose all that apply): Low Impact Criteria Review Whitepaper Priority (H/M/L): H Status: In progress. Forming team, scoping being finalized. | Security Guideline |  | Security Working Group (SWG) | Not Started | (1) High | Action on the guideline has been delayed due to limited availability of subject matter experts. | 0% | N/A | N/A | ​Risk Mitigation
Support the efforts of the BAL-003-1 SDT | Support the efforts of the BAL-003-1 SDT | Collaboration |  | Resources Subcommittee (RS) | In Progress | (2) Normal | In Progress - Is this the same as Item 9? | 50% | N/A | N/A | Performance Monitoring
Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms | Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms | Data Collection |  | Resources Subcommittee (RS) | In Progress | (2) Normal | This effort is still not fully scoped. | 50% | N/A | N/A | Performance Monitoring
Modeling and Simulations Technical Report. | Modeling and Simulations Technical Report. Findings, recommendations, and experiences modeling and studying inverter-based resources; information from NERC Alert data collection; generation interconnection studies; IRPTF stability studies | Reference Document |  | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal |  | 100% | Inverters | Model Fidelity | ​Risk Mitigation
Canyon 2 NERC Alert Follow Up | Canyon 2 NERC Alert Follow Up – Modeling and Simulation. Follow up work to ensure accurate and appropriate models are being used for local and interconnection-wide studies and base case creation. Engagement with MOD-032 Designees, Planning Coordinators, Transmission Planners, and Generator Owners to ensure accurate modeling. Follow up with the proposed changes and execution of those changes. | Review |  | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal |  | 100% | Inverters | Inverter - Other | ​Risk Mitigation
Reliability Guideline: Battery Energy Storage (BESS) and Hybrid Plant Performance and Modeling | Battery storage systems are increasing in size and number. Further, use of hybrid resources is increasing. There is lack of guidance and expertise on how to model and simulate these types of new resources in interconnection studies and planning assessments. The IRPTF will develop a reliability guideline that outlines recommended practices. | Reliability Guideline |  | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal |  | 100% | Bulk Power System Planning | Energy Storage | ​Risk Mitigation
Scope Review | Perform periodic scope review | Review |  | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Completed per RSTC approval on PAWG updated Scope doucment. | 100% | N/A | N/A | ​Reliability and Security Assessment
Reliability Guideline: DER Data Collection for Modeling. | Reliability Guideline: DER Data Collection for Modeling. Guideline providing recommendations and industry practices for the mandatory and optional DER data to be collected by the Reliability Coordinator as well as on how, where, and when to gather such data. | Reliability Guideline |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Approved by RSTC at October 2020 meeting. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Review of MOD-032-1 for DER Data Collection. | Review of MOD-032-1 for DER Data Collection. (In coordination with activity M4) White paper reviewing MOD-032-1 and providing potential modifications to the standard to facilitate data collection for DERs for interconnection-wide modeling. | Review |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | This item was completed with teh white paper approved by PC and the subsequent SAR also endoresed. The SAR then was sent to SC, where it was handled in that committee. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Frequency Monitor Reporting | Frequency Monitor Reporting (Standing RTOS agenda item to discuss) |  |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | On-going | 50% | N/A | N/A | Performance Monitoring
Coordination with SPIDERWG on DER models | Coordinated approach to adaptive UFLS (and UVLS) in the presence of substantial quantities of highly variable DER |  |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 70% |  |  | ​Risk Mitigation
6 GHz Task Force | The 6 GHz Task Force will provide recommendations to the NERC RSTC as follows: 1.Determine scope of issue (e.g., limited to 6 GHz, relationship to other telecommunications items, etc.) 2.Gather information related to risk of harmful interference in the 6 GHz spectrum. a.Identify penetration and Bulk Power System users relying on 6 GHz. b.Reach to industry for input on potential readiness issues (e.g., trade associations, membership organization, compliance forums, registered entities, etc.). c.Initiate or request industry information related to current harmful interference experience. d.Identify potential mitigation strategies. 3.Evaluate options for industry outreach. 4.Develop suggested recommendations related to the issue. | Recommendations |  | 6 GHz Task Force (6GHZTF)​ | In Progress | (2) Normal |  | 70% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems
Standards Committee Engagement | SPIDERWG Coodination subgroup task to provide technical support to Standards Committee Projects from SARs that originated in SPIDERWG.​ | Coordination |  | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | Ongoing coordination | 50% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
RS Review of Load Forecasting Impact on BAs | ​Balancing Authorities should have staff with specialized knowledge of how weather impacts load, including the effects of heat pump backup heating and other supplemental electric heating. Balancing Authorities should also broaden the scope of their near-term (seven-days prior to real-time) load forecast to include multiple models and sources of meteorological information to increase accuracy and should consider regional differences within their footprints. (Winter 2022-2023) | Review |  | Resources Subcommittee (RS) | In Progress | (2) Normal |  | 50% | Extreme Events | FERC-NERC Cold Weather Inquiry | Performance Monitoring
Review intermittent Generation to Improve Load Forecasts | ​In performing their near-term load forecasts, Balancing Authorities should analyze how intermittent generation affects their ability to meet the peak load (including the effects of behind-the-meter intermittent generation) (for the entire footprint as well as sub-regions, such as MISO South and SPP's southern region), especially if peak load cannot be met without variable resources. Balancing Authorities should consider performing a 50/50 or 90/10 forecast for renewable resources three-to -five days before real time. (Winter 2022-2023) | Analysis |  | Resources Subcommittee (RS) | In Progress | (2) Normal |  | 50% | Extreme Events | FERC-NERC Cold Weather Inquiry | Performance Monitoring
Work Plan item detailed description: White Paper: End-Use Load Electrification | ​Work Plan item detailed description: White Paper: End-Use Load Electrification |  |  | Reliability Security and Technology Committee (RSTC) | Not Started | (2) Normal |  | 0% | Inverters | Model Fidelity
Whitepaper: EV Charging & V2G Security Risks to BPS | Evaluate cybersecurity risks of EV charging and vehicle to grid technologies and architectures. Provide recommendations for standards, policies, and controls for industry. | Assessment |  | Security Integration and Technology Enablement Subcommittee (SITES) | Not Started | (2) Normal |  | 0% | Cyber Vulnerabilities | Cyber Security | ​Reliability and Security Assessment | N/A
CMLD Deployment (Phase2)-1 | Dynamic load model is implemented, tested and benchmarked in all production grid simulators - Siemens PTI PSS®E, General Electric PSLF, PowerWorld, and PowerTech TSAT | Implement | 4355500% | Load Modeling Working Group (LMWG) | Completed | (2) Normal | COMPLETED - Phase 1 of the model benchmarking is completed successfully in PTI PSS®E, GE PSLF, PowerWorld, and PowerTech TSAT | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
CMLD +DER Benchmarking Across Platforms | Composite Load Model + DER Benchmarking. Develop composite load model benchmarking notification to share with industry the completion and usability of the models across all major software platforms. | Benchmarking | 4361700% | Load Modeling Working Group (LMWG) | Completed | (2) Normal |  | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-01B | DER Models are implemented, tested and benchmarked as a part of the dynamic load model | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - Benchmarked DER Implementation, coordinated with SPIDER on DER modeling for dynamic load model, ensure that SPRIDER-develop models and data sets are updated in Load Model Data Tool | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
CMLD Deployment (Phase1)-02 | Load Model Data | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | Complete | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-02A | Mapping between powerflow Loads and "Load Type" Identifiers | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC Regions identified load climate<br>zones (airport codes) and corresponding "Load Type" identifiers, NERC Regions worked with Transmission Planners to develop mapping between power flow load buses and "Load Type" identifiers | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-02B | Load Composition Data Sets Developed | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC LMTF worked with DOE to develop 24-hour Load Composition Data Sets for 96 airport codes in NERC footprint for three seasons. | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-02C | Model Data for Large Industrial Loads | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC LMTF engaged industry experts to develop representative data sets for 20 types of industrial loads | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-02D | Robust Data Sets - End Use Data | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - Model data sets are developed based on extensive end-use testing and manufacturer's literature The data is stress-tested in PTI PSS®E and GE PSLF | 100% | Inverters | Model Fidelity | ​Risk Mitigation
CMLD Deployment (Phase1)-03 | Tools for Load Model Data management | Implement | 4364600% | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC Developed Load Model Data Tool for managing load model data and writing CMLD records in PTI PSS®E DYR and GE PSLF DYD formats. The tools are used to generate CMLD records for the field test and provided to NERC Regions | 100% | Inverters | Model Fidelity | ​Risk Mitigation
Review the UK final report for findings and recommendation’s that are applicable to the North American grid and present to the OC | Review the UK final report for findings and recommendation’s that are applicable to the North American grid and present to the OC |  | 4392100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Completed. Presented to the RSTC at the March 2020 meeting. | 100% | Inverters | Inverter - Other | Performance Monitoring
1-2020 Summer Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. Include seasonal scenarios to evaluate resource/energy adequcy risks in assessment areas. LTRA 2019 Rec 1 | Assessment | 4401200% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Complete. Published in May 2020. | 100% | N/A | N/A | ​Reliability and Security Assessment
5-Ramping Resource Analysis | Measure 6 Analysis White Paper documenting the results of screening analysis to identify areas with changes in their load patterns or their resource mix that could impact ramping and flexibility needs over time LTRA 2019 Rec 4 | Analysis | 4401200% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Complete. RAS approved white paper documenting results of pilot assessment and posted it on the RAS website. Methods such as the screening approach described in the white paper will be used to evaluate ramping concerns in future assessments. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Reliability and Security Assessment
5-Scope Review | Perform periodic scope review | Review | 4401200% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | RSTC approval requested in December 2020 | 100% | N/A | N/A | ​Reliability and Security Assessment
Annual Monitoring and Situational Awareness Conference | Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | Conference | 4410400% | EMS Working Group (EMSWG) | Completed | (2) Normal | The Monitoring and Situational Awareness Conference was held virtually across three sessions on 9/24, 10/15, and 11/10. | 100% | N/A | N/A | Performance Monitoring
Prepare for and facilitate the Annual Winter Weather Prep Webinar. | Prepare for and facilitate the Annual Winter Weather Prep Webinar. | Webinar | 4410400% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Annual webinar was held on 9/3/2020. | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | Performance Monitoring
Develop Lessons Learned | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. |  | 4410400% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% | N/A | N/A | Performance Monitoring
Annual review of CERTS/NERC (fnet, etc.) real-time applications. | Annual review of CERTS/NERC (fnet, etc.) real-time applications. | Analysis | 4410400% | Resources Subcommittee (RS) | Completed | (2) Normal | Annually | 100% | N/A | N/A | Performance Monitoring
Review and approval of the Annual Frequency Response Analysis Report during Q3 of each year. | Review and approval of the Annual Frequency Response Analysis Report during Q3 of each year. | Analysis | 4410400% | Frequency Working Group (FWG) | In Progress | (2) Normal | Complete for 2019 - NERC Staff Task, RS approval, OC Endorsement | 50% | N/A | N/A | Performance Monitoring
1-Review IRPWG Scope | Revised scope with new IRPWG group. | Review | 4419600% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal | Seeking approval at December 2020 RSTC meeting. | 100% | N/A | N/A | ​Risk Mitigation
2-San Fernando Disturbance Follow-Up | Discussion of NERC San Fernando Disturbance Report and identification of any next steps for IRPWG to add to work plan. | Review | 4419600% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal | IRPWG will meet in November to determine next steps. | 100% | N/A | N/A | ​Risk Mitigation
2-Long-Term Reliability Assessment | Annual Reliability Assessment Required by NERC RoP Sect 800. Includes probabilistic assessment (ProbA) to assess energy adequacy risk (LTRA Rec 1). Analysis is also underway to assess storage impacts on BPS (LTRA Rec 6)and transmission development trends/reliability risk (LTRA rec 7). LTRA 2019 Rec 1, 6, and 7 | Assessment | 4419600% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | RSTC Review Complete. Endorsement vote in progress November 2020. | 100% | Changing Resource Mix | Maintaining ERS Due to Retirements | ​Reliability and Security Assessment
3-Winter Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. Include seasonal scenarios to evaluate resource/energy adequcy risks in assessment areas. LTRA 2019 Rec 1 | Assessment | 4419600% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | RSTC Review Complete. Endorsement vote conducted November 2020. Published November 18. | 100% | N/A | N/A | ​Reliability and Security Assessment
2-Long-Term Reliability Assessment Enhancement | Develop screening approaches or other probabilistic studies to supplement LTRA in off ProbA years. LTRA 2019 Rec 1 | Assessment | 4419600% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Completed. | 100% | Changing Resource Mix | Maintaining ERS Due to Retirements | ​Reliability and Security Assessment
3-Probabilistic Assessment - Base Case | Perform biennial ProbA, sensitivity/scenario studies, for the 2020 LTRA LTRA 2019 Rec 1 | Assessment | 4419600% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Base ProbA included in 2020 LTRA. | 100% | N/A | N/A | ​Reliability and Security Assessment
Annual update to the RSTC of events, cause codes, trends, etc. | Annual update to the RSTC of events, cause codes, trends, etc. | Analysis | 4419600% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% | N/A | N/A | Performance Monitoring
Review and vet the Frequency Bias Settings and L10 values; scheduled to be implemented in April of each year. Repeated annual in accordance with the BAL-003-1 standard. | Review and vet the Frequency Bias Settings and L10 values; scheduled to be implemented in April of each year. Repeated annual in accordance with the BAL-003-1 standard. | Review | 4419600% | Frequency Working Group (FWG) | In Progress | (2) Normal | Ongoing | 50% | N/A | N/A | Performance Monitoring
Quarterly review of BA’s control performance. | Quarterly review of BA’s control performance. | Analysis | 4419600% | Resources Subcommittee (RS) | In Progress | (2) Normal | Ongoing | 50% | N/A | N/A | Performance Monitoring
Work Plan | Develop an SWG work plan for 2021 | Plan | 4425300% | Security Working Group (SWG) | Completed | (2) Normal |  | 100% | N/A | N/A | ​Risk Mitigation
V1-Reliability Guideline: DER Performance and Model Verification | Reliability Guideline covering aggregate DER model verification, including recommended measurement practices, executing model verification activities, model benchmarking, relation to MOD-033 activities, and conversion of data sources for verification. | Reliability Guideline | 4425700% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | Responded to Q4 2021 comment period. (High priority task for SPIDERWG) | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Scope Document | Develop Scope Document | Program | 4428600% | Security Working Group (SWG) | Completed | (2) Normal |  | 100% | N/A | N/A | ​Risk Mitigation
Load Model Composition : Initial data set | ​Load Composition Analysis (e.g, Buildings, end uses) | Analysis | 4434800% | Load Modeling Working Group (LMWG) | Completed | (2) Normal |  | 100% |  |  | ​Risk Mitigation
1-Data collection approaches and recommendations techincal report | Develop a technical report that describes industry approaches and best practices for probabilistic assessment | Data Collection | 4435500% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Approved by RSTC and posted to PAWG website for use | 100% | N/A | N/A | ​Reliability and Security Assessment
4-Probabilistic Assessment - Scenario Case | Develop and present findings in a Scenario report that expands upon the Base Case LTRA 2019 Rec 1 | Assessment | 4435600% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | RSTC approval in June 2021 / published | 100% | N/A | N/A | ​Reliability and Security Assessment
EGWG - Reliability Guideline Metrics | ​Develop a method to measure the Fuel Assurance Reliability Guideline effectiveness including the following goals set forth for 2021Run metrics and analysis around design basis for potential TPL 001 enhancements;Complete surveys and measurement criteria and results to determine efficacy of Fuel Assurance Guideline implemented in 2020Provide additional criteria for measuring effectiveness of 2017 Guideline: Gas and Electrical Operational ConsiderationsDevelop a summary of effectiveness of guidelines results that can be used to the purposes of SAR(s) or enhancements to existing guidelinesMonitor effectiveness of new GADS cause codes that provide for more visibility into root cause analysis of gas generator outages due to lack of fuel | Metrics | 4437700% | Electric Gas Working Group (EGWG) | Completed | (2) Normal | EGWG is holding monthly meetings and making progress on developing a survey as a measurement tool. | 100% | N/A | N/A | ​Risk Mitigation
5-White Paper: BPS-Connected IBR and Hybrid Plant Capabilities for Frequency Response | White paper on utilizing the full capabilities of inverter-based resources and hybrid plants for providing frequency response. | White Paper | 4437700% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal | New task; on track. | 100% | Inverters | IBR Frequency Response | ​Risk Mitigation
1- 2021 Summer Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4437700% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Complete. Published in May 2021. | 100% | N/A | N/A | ​Reliability and Security Assessment
Cloud Solutions and Encrypting BCSI | Implementation guidance for BES Cyber System Information in the cloud | Compliance Guidance | 4437700% | Security Working Group (SWG) | Completed | (2) Normal |  | 100% | Cyber Vulnerabilities | Encryption in the Cloud | ​Risk Mitigation
Review & Input into EA Chapter of 2021 SOR | Develop EA Chapter of the State of 2021 Reliability Report in coordination with PAS. | Report | 4440800% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% | N/A | N/A | Performance Monitoring
2021 Winter Weather Prep Webinar | ​Prepare for and facilitate the annual winter weather prep webinar | Webinar | 4444100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Status set to 99% since the Webinar will be completed prior to the September RSTC Meeting. | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | Performance Monitoring
Complete Assessing and Reducing Risks Tool | Update tool and support document based on 45-day commenting from industry, deliver for final approval | Reference Document | 4446900% | Security Working Group (SWG) | Completed | (2) Normal | Documents are posted. Announcement with link to Technical Reference Document, Tool, and a Survey has been sent. Survey responses are due 9/30/2021 | 100% | N/A | N/A | ​Risk Mitigation
Annual Monitoring and Situational Awareness Conference | ​ Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | Conference | 4449700% | EMS Working Group (EMSWG) | Completed | (2) Normal | The Monitoring and Situational Awareness Conference was held virtually on 9/23, 10/07, and 10/28. | 100% | N/A | N/A | Performance Monitoring
3- 2021-2022 Winter Reliability Assessment | ​Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4453000% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | The WRA was published on November 18. | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Reliability and Security Assessment
M1-DER Modeling Survey | Perform industry survey of SPIDERWG members regarding use of DER planning models in BPS studies, dynamic load models and DER modeling guidelines. | White Paper | 4454400% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | White Paper approved at December 2021 RSTC | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Technical Report on Methods for Analyzing and Mitigating Forced Oscillations | To address potential reliability impacts from forced oscillation events (e.g., January 2019 EI event), SMWG will provide guidance on how RC/TOPs can determine the quantities to be monitored, thresholds to be monitored and the corresponding mitigation actions for consistency in developed operating procedures and mitigation plans. | White Paper | 4454400% | Synchronized Measurement Working Group (SMWG) | Completed | (2) Normal | Document has been posted on NERC.com | 100% | N/A | N/A | Performance Monitoring
2- 2021 Long Term Reliability Assessment | ​Annual Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4454700% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Publication planned for mid-December. | 100% | Changing Resource Mix | Maintaining ERS Due to Retirements | ​Reliability and Security Assessment
Develop Lessons Learned in 2021 | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. | Industry Engagement | 4456100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | 12 Lessons Learned were published in 2021. RSTC dropped the need for "training" sessions. Summary presentations of newly published LLs were provided for RSTC agendas. A Battery Fire LL presentation to the RSTC was made. Winter Webinar referenced prior LLs | 100% | N/A | N/A | Performance Monitoring
Analysis of cause codes looking for common threads and trends. | Analysis of cause codes looking for common threads and trends. Provide update to RSTC on trends, threads, etc. as required | Analysis | 4456100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | A detailed analysis of identified root causes for EAP qualified events for the previous year (2020) was performed as part of the State of Reliability development effort. (See 2021 SOR Fig 2.4, Fig 2.5, & Fig 2.6). | 100% | N/A | N/A | Performance Monitoring
Events Analysis Process Review and Update | Events Analysis Process Review and Update | Analysis | 4456100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | A comprehensive periodic review of the Event Analysis Process (EAP) is scheduled for 2022. In 2021 the EAS made considerable progress in addressing major specific items that will be used in the 2022 comprehensive review. | 100% | N/A | N/A | Performance Monitoring
Develop Lessons Learned Webinars | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. |  | 4456100% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Duplicate of task 271. Winter Webinar referenced prior LLs. | 100% | N/A | N/A | Performance Monitoring
Develop SAR to consolidate Glossary definitions of ACE | Develop SAR to consolidate Glossary definitions of ACE | SAR/RFI | 4456100% | Resources Subcommittee (RS) | Completed | (2) Normal | RSTC Endorsed the SAR in December 2021 and is being presented to the SC in January 2022. | 100% | N/A | N/A | Performance Monitoring
Coordinated Review of NERC Reliability Standards | Develop a technical report outlining a roadmap to ensuring BPS reliability under increasing penetration of inverter-based resources; discussion of issues and possible solutions to these issues. | Review | 4456100% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal | Completed in 2020 by IRPTF | 100% | Inverters | Increased Penetration of Renewables | ​Risk Mitigation
Energy Reliability Assessment Task Force (ERATF) | The task force will look atenergy availability concerns related to operations, operations planning and mid-to-long-term planning horizons. The scope and work plan will be created and sent to the RSTC. | Coordination | 4456100% | Energy Reliablity Assessment Task Force (ERATF) | Completed | (2) Normal |  | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Develop external website organization and content | Develop organization and content for the SWG external website (new) along with process for publishing (including approvals). This includes leveraging tools to collect input from industry. | Webinar | 4456100% | Security Working Group (SWG) | Completed | (2) Normal |  | 100% | N/A | N/A | ​Risk Mitigation
EGWG Gas-Electric Planning Basis (N-1) | Develop information that will inform work to create a Reliability Standard for natural gas planning criteria.​ | Analysis | 4456100% | Electric Gas Working Group (EGWG) | Completed | (2) Normal | EGWG had their last meeting for 2021 on December 8. The design basis is at a point it can be reviewed by others. | 100% | Natural Gas | Increased Dependency on Natural Gas | ​Risk Mitigation
S4A-Reliability Guideline: Recommended Approaches for Developing Underfrequency Load Shedding Programs with Increasing DER Penetration | Guidance on how to study UFLS programs and ensure their effectiveness with increasing penetration of DER represented | Reliability Guideline | 4459900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Approved at December 2021 RSTC | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Review Cold weather Tiger Team Recommendations | Review and determine which recommendations the Cold Weather Tiger Team can/should be implemented by the SPCWG, with the recommendations added to the SPCWG work plan if appropriate​ |  | 4460300% | System Protection and Control Working Group (SPCWG) | Completed | (2) Normal | The SPCWG response was provided to Steve Crutchfield on Feb 11, 2022 | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Risk Mitigation
S2a-SAR: Updates to TPL-001 Regarding DER Considerations | Sub-team is developing a SAR that incorporates the recommendations put forth in the approved white paper, considering the items that need standards revisions to improve reliability. This activity will also be coordinated with IRPWG to address the issues identified in their recently approved white paper identifying issues with TPL-001. | SAR/RFI | 4463500% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | SAR endorsed at December 2021 RSTC. Awaiting approval of SC | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Inverter-based Resources Impacts to BPS Protection Systems | Inverter-based Resources Impacts to BPS Protection Systems Transmission protection practices and systems will need to adapt to the changing nature of the grid. SPCS will develop a technical report on the impacts that BPS-connected inverter-based resources can and are having on BPS protection systems. The report will be coordinated with NERC Inverter-Based Resources Performance Working Group (IRPWG), as needed, to bring protection and inverter experts together. The intent of the technical report is to provide a framework, roadmap, and technical guidance for industry to tackle this challenge. | Analysis | 4465200% | System Protection and Control Working Group (SPCWG) | Deferred | (3) Low | This task will be closed and the SPCWG will monitor and support the IEEE project. If it is determined that the IEEE project is no longer sufficient to cover this task, it can be reopened at a later date. | 100% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
1- 2022 Summer Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4469900% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Report published. | 100% |  |  | ​Reliability and Security Assessment
Parallel Flow Visualization tool | RTOS to act as lead on development of, and recommendation to implement, Parallel Flow Visualization tool | Influence | 4471400% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Q3 2022 | 100% | N/A | N/A | Performance Monitoring
S3-Recommended Simulation Improvements and Techniques | Develop and provide guidance to software vendors on simulation improvements on DER. | Outreach | 4471900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Completed vendor engagement and working to respond to RSTC in 2022 | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Reliability Coordinator Plan Reference Document | Reliability Coordinator Plan Reference Document |  | 4472000% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Q2 2022 | 100% | N/A | N/A | Performance Monitoring
GMD Monitoring Reference Document | GMD Monitoring Reference Document | Reference Document | 4472000% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Approved by the RSTC | 100% |  |  | Performance Monitoring
RISC Cold weather Recommendation 13 - SPCWG | he SPCWG will review and provide a recommendation to the GADS user's group on what type of information/aplification would be useful to evaluate how units trip due to high rate-of-change of frequency conditions or extended low frequency conditions. The GADS user's group would then be responsible for the implementation of that recommendation or not. The SPCWG will provide a recommendation to the GADS User Group by Mid June, 2022 ​ | Assessment | 4472200% | System Protection and Control Working Group (SPCWG) | Completed | (1) High | On track. The SPCWG has approved the small group plan and has sent to Steve Crutchfield. Will review at June RSTC meeting | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Risk Mitigation
V2-Reliability Guideline: DER Forecasting Practices and Relationship to DER Modeling for Reliability Studies | Guidance providing how forecasting practices are linked to DER modeling for reliability studies. DER forecasting practices are important for accurately representing the correct amount and type of DER, particularly at an aggregate level representation for BPS studies. | Reliability Guideline | 4472700% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Responding to industry comments from Period in late 2021. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
ERATF SARs | ​In December 2021, he ERATF created a SAR and submitted it to the RSTC. Comments due back by January 14, 2022. Extensive outreach was conducted during Jan - June, and comments were solicited from MRC Policy Input (Jan 2022), an industry workshop (Feb 2022). The ERATF revised the SAR and created two - one for the Operations time frame and a second SAR for the Planning time frame. In addition, the technical justification was revised (Appendix A) and key terms were defined (Appendix B). The revisions were described during a webinar (May 2022). The two SARs were submitted to the RSTC for technical endorsement (June 2022), then were submitted for SC acceptance (June 2022). | Collaboration | 4472700% | Energy Reliablity Assessment Task Force (ERATF) | Completed | (1) High |  | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
2022 State of Reliability Report | ​Play a lead role in the development of the 2022 State of Reliability Report in coordination with the PAS including, but not limitied to, the analysis of cause codes and identification of trends for qualifying events in accordance with the EAP. | Report | 4474300% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% |  |  | Performance Monitoring
2022 State of Reliability Report (SOR) | Rules of Procedure Section 800 states that NERC will: “conduct and report the results of an independent assessment of the overall reliability and adequacy of the interconnected North American Bulk Power Systems, both as existing and as planned” and “develop reliability performance benchmarks. The final reliability assessment reports shall be approved by the Board for publication to the electric industry and the general public” *Rules of Procedure -https://www.nerc.com/FilingsOrders/us/RuleOfProcedureDL/NERC_ROP_Effective_20190125.pdf - Section 800 | Assessment | 4476200% | Performance Analysis Subcommittee (PAS) | Completed | (2) Normal | 7/7: Board accepted | 100% | N/A | N/A | Performance Monitoring
Reliability Guideline: Forced Oscillations | Reliability Guideline: Forced Oscillations | Reference Document | 4478400% | Synchronized Measurement Working Group (SMWG) | Completed | (2) Normal | Document has been posted on NERC.com | 100% | N/A | N/A | Performance Monitoring
Security Guideline: Physical Security Considerations at High Impact Control Centers | Add Metrics; place on RG/SGTemplate | Security Guideline | 4478500% | Security Working Group (SWG) | Not Started | (2) Normal | Add Metrics; place on RG/SG template. Original due date of Q3/Q4 2022 delayed due to uncertainty about responsibility (SWG or E-ISAC) | 0% | N/A | N/A | ​Risk Mitigation
Security Guideline: Physical Security Response | Add Metrics; place on RG/SGtemplate Q3/Q4 2022 | Security Guideline | 4478500% | Security Working Group (SWG) | Not Started | (2) Normal | Add Metrics; place on RG/SG template. Original due date of Q3/Q4 2022 delayed due to uncertainty about responsibility (SWG or E-ISAC) | 0% | Physical Vulnerabilities | Physical Security - Other | ​Risk Mitigation
Security Guideline: Reliability Assessments and Resiliency Measures for Extreme Events | Add Metrics; place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4478500% | Security Working Group (SWG) | Not Started | (2) Normal | Add Metrics; place on RG/SG Template Q3/Q4 2022 | 0% | N/A | N/A | ​Risk Mitigation
RISC Cold weather Recommendation 22 - SPCWG | ​The SPCWG will review PRC-006-5 and determine if there is a need to make a change to PRC-006-5 to account for time based underfrequency generation tripping and provide a recommendation on what those changes could entail by August 12, 2022. | Assessment | 4478800% | System Protection and Control Working Group (SPCWG) | Completed | (1) High | Recommendation: It is not necessary to revise the Reliability Standard PRC-006-5. Instead, where adequate time for manual intervention exists, it should be addressed by manual balance of load/generation . Recommend to consult RTOS | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Risk Mitigation
S5-White Paper: Beyond Positive Sequence RMS Simulations for High DER Penetration Conditions | Considerations for high penetration DER systems and the need for more advanced tools (e.g., co-simulation tools) for studying DER impacts on the BPS. | White Paper | 4481800% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | On track. Draft nearing completion. Subgroup still in discussion on final touches of draft. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
C6-NERC Reliability Standards Review White Paper | White Paper reviewing NERC Reliability Standards and impacts of DER. | White Paper | 4481800% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | Initial reviews complete, consolidating responses into draft white paper; white paper in review by SPIDERWG subgroup. Needs RSTC review prior to approval. Tagged one relevant Cold Weather recommendation | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
S4B-White Paper: DER Impacts to UVLS Programs | Short white paper on potential impacts of DERs on UVLS program design; leverage work of PRC-010 standards review (C6 task). | White Paper | 4481900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Responding to RSTC Review in Q2 2022 | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Improved Three-Phase Motor Model | Improved Three-Phase Motor Model | Research | 4486500% | Load Modeling Working Group (LMWG) | Completed | (2) Normal |  | 100% | Inverters | Model Fidelity | ​Risk Mitigation
Capacitor tripping in CMLD Model | ​Capacitor tripping in CMLD Model | Evaluation | 4486500% | Load Modeling Working Group (LMWG) | Completed | (2) Normal |  | 100% |  |  | ​Risk Mitigation
Time Monitors | Notify RSTC of Time Monitors for 2022 and 2023 | Monitor | 4487600% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Q4 Annually | 100% | N/A | N/A | Performance Monitoring
GMD Monitors | Notify RSTC of changing GMD Monitors | Monitor | 4487600% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Q4 Annually - SPP GMD monitor for 2022 | 100% | N/A | N/A | Performance Monitoring
Security Guideline: Risk Management Lifecycle | Revise content, add metrics; place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4487600% | Supply Chain Working Group (SCWG) | In Progress | (2) Normal | Revised content includes added metrics; to be published on RG/SG Template Q3/Q4 2022 | 75% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
Security Guideline: Secure Equipment Delivery | Revise content; add metrics; place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4487600% | Supply Chain Working Group (SCWG) | In Progress | (2) Normal | Revised content includes added metrics; to be published on RG/SG Template Q3/Q4 2022 | 75% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
Security Guideline: Vendor Risk Management Lifecycle | Revise content and add metrics; place on RG/SG Template Q3/Q4 2022 | Security Guideline | 4487600% | Supply Chain Working Group (SCWG) | In Progress | (2) Normal | Add Metrics; place on RG/SG Template Q3/Q4 2022 | 75% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
Reliability Guideline: Power Plant Model Verification using PMUs | Reliability Guideline: Power Plant Model Verification using PMUs | Reference Document | 4487600% | Synchronized Measurement Working Group (SMWG) | Completed | (2) Normal | Document has been posted on NERC.com | 100% | N/A | N/A | Performance Monitoring
Section 1600 Data Request for GADS | NERC RoP GADS Section 1600 Data Reporting to collect GADS data: • Conventional - relevant design data and enhanced event reporting • Wind - connected energy storage and event reporting • Solar - plant configuration, performance and event data as well as equipment outage detail | Data Collection | 4488000% | Performance Analysis Subcommittee (PAS) | Completed | (2) Normal | The NERC Board of Trustees approved the GADS Section 1600 Data Request at the November 15-16, 2022 Board meeting. The GADS Section 1600 changes will become effective in 2024.​ | 100% | Changing Resource Mix | Changing Resource Mix | Performance Monitoring
2022-2023 Winter Reliability Assessment | ​ Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4489700% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | This assessment was published on November 17. | 100% |  |  | ​Reliability and Security Assessment
Determine whether or not to implement Cold weather Tiger Team Recommendation 13 | ​Add Generating Availability Data Source Cause Code Amplification Code for outages related to frequency deviation. The GADS User Group Leadership has advised NERC staff that the ability of a GADS reporter to distinguish the type of event that may have tripped a unit on frequency is generally quite limited. This type of determination typically requires a very detailed post-event analysis, including examination of the inner working of the relay's programmed scenarios. After considering development of a GADS amplification code for outages related to frequency deviation, the GADS User Group recommends, and NERC staff agree, that a frequency event cause code be developed and reported upon the operation of a Type 81 relay. Although further analysis to determine why an 81 relay target dropped is subsequently performed, e.g., Reliability Standards require that relay operation be reviewed to verify correct operation; this is not a GADS reporting function. The use of a GADS cause code would indicate an impact to generation to facilitate the post-event analysis in connecting with other data collected during a frequency event. This recommendation will be presented to the GADSUG for acceptance at the November 22, 2022 meeting. | Data Collection | 4490100% | Performance Analysis Subcommittee (PAS) | Completed | (2) Normal | November: Generating Availability Data (GADS) User Group accepted recommendation to add a cause code related to frequency deviation. December: RSTC to be informed of progress to date. PAS to vote on whether or not to approve the GADSUG recommendation. | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | Performance Monitoring
Security Guideline: Open Source Software | Revise/update content; add metrics; place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4490200% | Supply Chain Working Group (SCWG) | Completed | (2) Normal | Guideline approved at RSTC meeting, December 2022 | 100% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
A1 - Reliability Guideline Review: Tranche 2 | ​The Analysis team to combine the three DER modeling reliability guidelines to submit a single guideline per the RSTC's Triennial review approved in December 2021. | Reliability Guideline | 4490300% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | Part of the RSTC RG review | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
M6-Modeling Distributed Energy Storage and Multiple Types of DERs | SPIDERWG will dig into technical considerations of modeling distributed energy storage, specifically distributed battery energy storage (D-BESS). The group will also consider how to model multiple types of DERs, including D-BESS and distributed solar PV (D-PV). Lastly, the group will focus on forecasting and dispatch assumptions for D-BESS. SPIDERWG will determine the level of guidance or reference materials needed once discussions begin. Task to be coordinated with Studies sub-group. | Reliability Guideline | 4490800% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High | Subgroup setup to begin drafting. Drafting underway. Lowered priority due to comprehensive RG review. | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
2- 2022 Long Term Reliability Assessment | Annual Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4490900% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | The report was published on December 15. | 100% | N/A | N/A | ​Reliability and Security Assessment
Periodic Review of Supply Chain Security Guidelines | Supply Chain Security Guidelines have been developed for industry and are scheduled for periodic reviews. | Review | 4490900% | Supply Chain Working Group (SCWG) | In Progress | (2) Normal | Five Supply Chain Security guidelines are scheduled for content review and revised if necessary. | 25% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
State of Technology Report | Technical report providing industry with strategic guidance regarding new or emerging technology solutions and risk-based considerations for their successful implementation. (Scope Activity Technology Enablement #1) | Reference Document | 4492500% | Security Integration and Technology Enablement Subcommittee (SITES) | On Hold | (2) Normal | Initial work plan item for team consideration. | 10% | Cyber Vulnerabilities | Cyber - Other | ​Reliability and Security Assessment
SITES Industry Workshop | An industry-wide technical workshop (likely remotely) to highlight strategic areas of focus related to new technologies, technology enablement, and security integration. (Scope Activity Technology Enablement #2) | Workshop | 4492500% | Security Integration and Technology Enablement Subcommittee (SITES) | On Hold | (2) Normal | There has been discussion about holding an industry workshop but group members have primarily focused on other projects so workshop plans remain tentative. | 10% | Cyber Vulnerabilities | Cyber - Other | ​Reliability and Security Assessment
Reliability / Security Guideline: Integration of Cyber and Physical Security with BPS Planning, Operations, Design, and System Restoration | Recommendations for industry regarding ways that BPS planning, operations, design, and restoration activities can be enhanced by considering cyber and physical security aspects to improve BPS reliability and resilience; recommendations regarding the convergence of IT and OT networks. (Scope Activity Security Integration #1 and #2) | Reliability Guideline | 4492500% | Security Integration and Technology Enablement Subcommittee (SITES) | On Hold | (2) Normal | Task will be addressed as volunteers become available and higher priority projects are completed. | 10% | Physical Vulnerabilities | Cyber and Physical Security into BPS Planning | ​Reliability and Security Assessment
White Paper: Review and Enhancement of Cybersecurity Maturity Metrics | Review and enhance the development of metrics to track the capabilities and maturity of cybersecurity and its integration with BPS reliable operation on a broad level; considerations at a macro-scale, integrating all aspects of overall BPS security, reliability, and resilience. (Scope Activity Security Integration #3 and #5) | Reference Document | 4492500% | Security Integration and Technology Enablement Subcommittee (SITES) | On Hold | (2) Normal |  | 50% | Cyber Vulnerabilities | Cyber - Other | ​Reliability and Security Assessment
White Paper: Risk-Based Physical and Cybersecurity Threats and their Impacts to BPS Reliability and Resilience | Guidance and reference materials providing information about security threats and how Registered Entities can plan, design, and operate the system to mitigate these potential risks. High-level recommendations for industry to consider in their own engineering and security practices for mitigating potential BPS reliability risks. Considerations for generation, transmission, and distribution-level risks as well as such as the natural gas infrastructure, and end-use (Scope Activity Security Integration #4) | Reference Document | 4492500% | Security Integration and Technology Enablement Subcommittee (SITES) | On Hold | (2) Normal | Document remains on the work plan but the group's focus on other projects has delayed further action. | 25% | Physical Vulnerabilities | Physical Security - Other | ​Reliability and Security Assessment
SAR PRC-025-2 Hybrid Plants | The SPCWG will be working on understanding the issue with calculating pick up setting for dispersed generation resources. For example, one issue is the addition of energy storage which increases the plant total MVA or overbuilding capacity to help meet contracted outputs on less than optimal days. | SAR/RFI | 4492600% | System Protection and Control Working Group (SPCWG) | Completed | (2) Normal | Stakeholder was unresponsive to requests for additional information. | 100% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
Annual Monitoring and Situational Awareness Conference 2022 | ​ Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | Conference | 4492600% | EMS Working Group (EMSWG) | Completed | (2) Normal | Session 1 was on 9/22, Session 2 was on 10/6, and Session 3 was 10/20 | 100% | Human Performance and Skilled Workforce | Loss of Situational Awareness | Performance Monitoring
Biennial Review of the Risk and Mitigations for Losing EMS Functions Reference Document | ​Biennial Review of the Risk and Mitigations for Losing EMS Functions Reference Document to be Endorsed by the RSTC |  | 4492600% | EMS Working Group (EMSWG) | Completed | (2) Normal |  | 100% | Human Performance and Skilled Workforce | Loss of Situational Awareness | Performance Monitoring
Develop & Publish Lessons Learned in 2022 | ​ Play a lead role in the development and endorsement of Lessons Learned to be published by NERC. This could include the facilitation of Lessons Learned webinars to increase industry awareness, as appropriate. | Industry Engagement | 4492600% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Thirteen Lessons Learned were developed and published in 2022 | 100% |  |  | Performance Monitoring
Failure Modes and Mechanism Diagrams for 2022 | ​​Play a lead role in the development of Failure Modes and Mechanism Diagrams supporting the EA Program's Addendum for Events with Failed Station Equipment. This is accomplished through the EAS subgroup FMMTF. |  | 4492600% | Failure Modes and Mechanisms Task Force (FMMTF) | Completed | (2) Normal | The FMMTF created three new FMM diagrams and revised several others in 2022. | 100% |  |  | Performance Monitoring
Annual Winter Weather Webinar 2022 | ​Play a lead role in the facilitation of the Winter Weather Webinar in the Fall of 2022 |  | 4492600% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | The Winter Weather Webinar was conducted on September 1, 2022 | 100% |  |  | Performance Monitoring
Support the RISC Report Recommendations re: Extreme Weather Events as Requested | ​Support the RISC Report Recommendations re: Extreme Weather Events as Requested by the RSTC and/or Recommendation Lead Group. This could include, but is not limited to, provide support in the development of historic extreme events and participation in a future Resiliency Task Force. |  | 4492600% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% |  |  | Performance Monitoring
Support the FERC/NERC joint inquiry recommendations on cold weather outages as Requested | ​Support the FERC/NERC joint inquiry recommendations on cold weather outages in ERCOT, MISO, and SPP, as requested by the RSTC and/or Recommendation Lead Group. This could include, but is not limited to, participation in any SAR and/or Standard Drafting Teams. |  | 4492600% | Event Analysis Subcommittee (EAS) | Completed | (2) Normal |  | 100% |  |  | Performance Monitoring
EGWG Follow up #8 on the February 2021 Cold Weather Grid Operations | ​ ​February 2021 Cold Weather Grid Operations: Final Findings and Recommendations, FERC, NERC and Regional Entity Joint Staff Inquiry | White Paper | 4492600% | Electric Gas Working Group (EGWG) | Completed | (2) Normal |  | 100% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Risk Mitigation
Whitepaper: Cybersecurity for DERs and DER Aggregators | An informational whitepaper to provide industry with guidance regarding activities in the area of cybersecurity for distributed energy resources (DERs) and DER Aggregators. Specifically, IEEE 1547.3 cybersecurity guidance for DERs, and UL certification for device level security of DERs. Written in collaboration with NREL and UL, with input and edits from SITES. | White Paper | 4492600% | Security Integration and Technology Enablement Subcommittee (SITES) | Completed | (2) Normal | Submitted to December2022 RSTC agenda for Request for Approval | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Reliability and Security Assessment
13-​SAR EOP-004-4 | ​SAR: EOP-004-4 Gen Loss Criteria for IBRs | SAR/RFI | 4492600% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal |  | 100% | Inverters | Inverter - Other | ​Risk Mitigation
18-SAR: IBR Performance Issues | ​IRPS will develop a SAR regarding either revisions to PRC-004 or a new standard that focuses specifically on analyzing, reporting, and correcting the abnormal performance of BES generating resources. These revisions may link with those identified above regarding the performance validation standard. Both topics may be accomplished with a singular SAR. | SAR/RFI | 4492600% | Inverter-Based Resource Performance Subcommittee (IRPS) | Completed | (2) Normal |  | 100% |  |  | ​Risk Mitigation
Security Guideline: Primer for Cloud Solutions and Encrypting BCSI | Add Metrics; place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4496000% | Security Working Group (SWG) | Not Started | (2) Normal | Add Metrics; place on RG/SG Template Q3/Q4 2022 | 0% | N/A | N/A | ​Risk Mitigation
6-Reliability Guideline: EMT Modeling and Studies | Reliability Guideline: Electromagnetic Transient Modeling and Simulations | Reliability Guideline | 4498600% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 70% | Inverters | Model Fidelity | ​Risk Mitigation
Address issues identified in FERC CIP002 Lessons Learned from Commission-Led CIP Reliability Standards audits | Review the Lessons Learned document that FERC staff published and share relevant observations with industry | Benchmarking | 4499400% | Security Working Group (SWG) | Completed | (2) Normal | The team has completed its draft report, which is now being reviewed before submission to RSTC | 100% | N/A | N/A | ​Risk Mitigation
Security Guideline: Cloud Computing | Revise to add metrics and place on RG/SG Template Q3/Q4 2022 | Security Guideline | 4499400% | Supply Chain Working Group (SCWG) | Not Started | (2) Normal | Revised content will be limited to added metrics and published on RG/SG Template Q3/Q4 2022 | 0% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
Security Guideline: Provenance | Revise/update content; add metrics; place on RG/SG template Q3/Q4 2022 | Security Guideline | 4499400% | Supply Chain Working Group (SCWG) | Not Started | (2) Normal | Revise content, to include added metrics; to be published on RG/SG Template Q3/Q4 2022 | 0% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
Security Guideline: Vendor Incident Response | Revise to add metrics and place on RG/SGTemplate Q3/Q4 2022 | Security Guideline | 4499400% | Supply Chain Working Group (SCWG) | Not Started | (2) Normal | Revised content will be limited to added metrics and published on RG/SG Template Q3/Q4 2022 | 0% | Cyber Vulnerabilities | Supply Chain | ​Risk Mitigation
C9 Reliability Guideline Review: Tranche 3 | The Coordination team to review the BPS Reliability Perspectives on the Adoption of 1547-2018 reliability guideline per the RSTC's Triennial review approved in December 2021.​ | Reliability Guideline | 4499900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High |  | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
SPIDERWG FAC-001 SAR | ​SAR FAC-001-3 | SAR/RFI | 4499900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (1) High |  | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
SPIDERWG FAC-002 SAR | ​SAR FAC-002-2 Revise Standard to ensure responsible entities study DER impacts to T-D Interface | SAR/RFI | 4499900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal |  | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
A2 - Reliability Guideline Review: Tranche 3 | ​The Analysis team to combine the DER Model verification and DER Data collection reliability guidelines to submit a single guideline per the RSTC’s Triennial review approved in December 2021 | Reliability Guideline | 4500500% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal | Drafting and Merge started. In review | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Reliability Guideline: Cyber Intrusion Guide for System Operators | Reliability Guideline: Cyber Intrusion Guide for System Operators (Approved by the Operating Committee on June 5, 2018) | Reliability Guideline | 4500700% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Posted on NERC.com | 100% | Cyber Vulnerabilities | Cyber Intrusion | Performance Monitoring
Reliability Guideline: Gas and Electrical Operational Coordination Considerations | Reliability Guideline: Gas and Electrical Operational Coordination Considerations | Reliability Guideline | 4500700% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Posted on NERC.com | 100% | N/A | N/A | Performance Monitoring
R-21 Improve rotational load shed plans in collaboration with RAS | Provide further guidance |  | 4500700% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | Submiited RTOS response to RSTC | 100% |  |  | Performance Monitoring
R-20: Perform bi-directional seasonal transfer studies for training | Provide further guidance |  | 4500700% | Real Time Operating Subcommittee (RTOS) | Completed | (2) Normal | RAS has lead - nothing for RTOS to do | 100% |  |  | Performance Monitoring
Bulk Power System (BPS) Performance Expectations for electromagnetic pulse (EMP) events (EMPWG work plan item 5) | ​Establish performance expectations for all sectors of the BPS regarding a predefined electromagnetic pulse (EMP) event. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Policy subteam of the EMPWG. Day to day job responsibilities have made it difficult for many EMPWG members to be available as subject matter experts to the group. As a result, work plan deadlines have been missed or changed. The EMPWG is e | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Industry and Public Education about electromagnetic pulse (EMP) threats (EMPWG work plan item 6) | ​Develop (or reference) educational material about EMP events and their impact on intelligent electronic devices and BPS reliability. | White Paper | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Policy subteam of the EMPWG. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is eval | 15% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Coordination with Other Sectors about Electromagnetic Pulse (EMP) issues and activities (EMPWG work plan item 7) | ​Develop guidance for the electricity industry about coordinating with interdependent utility sectors | Guidance | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal |  | 15% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Electromagnetic Pulse (EMP) Research Gaps (EMPWG work plan item 8) | ​Support additional research to close existing knowledge gaps into the complete impact of an EMP event to understand vulnerabilities, develop mitigation strategies, and plan response and recovery efforts | Analysis | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Research and Development subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Monitor research and development initiatives pertaining to electromagnetic pulse (EMP) threats (EMPWG work plan item 9) | Provide information to industry about current research pertaining to EMP and EMP-related national security initiatives that impact the BPS | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Research and Development subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Hardening Equipment to mitigate effects of Electromagnetic Pulse (EMP) (EMPWG work plan item 10) | ​Support efforts to design equipment specifications for the electric sector utility industry that address EMP hardening and mitigation strategies | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Research and Development subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Tools and Methods for assessing Electromagnetic Pulse (EMP) vulnerabilities | ​Support development of tools and methods (and make available) for system planners and equipment owners to use in assessing EMP impacts on the BPS. (EMPWG work plan item 11) | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Vulnerability Assessment subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Critical Asset Identification: Identifying Assets that (EMPWG work plan item 12) | ​Develop guidance for identifying and prioritizing assets that should be hardened so the Bulk Power System can be maintained and restored if an EMP event occurs. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Vulnerability Assessment subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is | 25% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Enhance Operating Plans and Procedures to address EMP (EMPWG work plan item 17) | ​Develop EMP event criteria that industry can incorporate into operating plans, operating procedures, and system restoration plans. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Response and Recovery subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is ev | 50% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Strategies for Supporting Recovery from EMP Events (EMPWG work plan item 14) | ​Develop training for system and plant operators about EMP events and what to anticipate and incorporate EMP events in industry exercises to test response planning and system restoration recovery efforts. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Response and Recovery subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is ev | 50% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Response Planning for EMP events (EMPWG work plan item 16) | ​Develop response planning guidelines for electric utility industry members for pre and post-contingency of an EMP event that aligns with plans of applicable regulatory authorities. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Response and Recovery subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is ev | 50% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
Incorporate EMP Events into Industry Exercises and Training (EMPWG work plan item 18) | ​Develop training for system and plant operators about EMP events and what to anticipate and incorporate EMP events in industry exercises to test response planning and system restoration recovery efforts. | Reference Document | 4501600% | Electromagnetic Pulse Working Group (EMPWG) | In Progress | (2) Normal | Assigned to the Response and Recovery subteam. Day to day job responsibilities have made it difficult for EMPWG members to offer subject matter expertise to the group's efforts. As a result, work plan deadlines have been missed or changed. The EMPWG is ev | 50% | Physical Vulnerabilities | Electromagnetic Pulse (EMP) | ​Risk Mitigation
1- 2023 Summer Reliability Assessment | ​Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4506300% | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | RSTC review in progress through May 3rd. The expected publication is in mid-May. | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Whitepaper: Zero Trust for OT Cybersecurity | Define. Identify benefits, risks, challenges. Illustrate architecture. Provide guidelines and recommendations for adoption and CIP considerations. | White Paper | 4507700% | Security Integration and Technology Enablement Subcommittee (SITES) | Completed | (2) Normal | Receiving RSTC comments and making final edits | 100% | Cyber Vulnerabilities | Cyber Security | ​Reliability and Security Assessment
ERATF Work Plan #1: White Paper – Overview of Energy Reliability Assessments – Volume 1 | ​Explain the what, the why, and the elements of an energy reliability assessment, including ancillary services. | White Paper | 4507700% | Energy Reliablity Assessment Task Force (ERATF) | Completed | (2) Normal |  | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
20-Assessment: Gap Analysis of Any IBR-Related Issues Not Addressed by NERC Standards | ​IRPS will conduct a comprehensive assessment, considering all guidelines and technical reference documents developed thus far, including IEEE P2800, to determine any performance gaps not addressed by the NERC Reliability Standards and will provide recommendation for additional SARs, where applicable. Any modifications will seek to ensure the same outcome across resource types and ensure a similar intent is met with the language used in each standard requirement. | White Paper | 4507800% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% |  |  | ​Risk Mitigation
22-Grid Forming White Paper Follow-Up | ​Follow-on activity to previously published IRPS white paper on grid forming, focused specifically on leveraging GFM technology in battery energy storage projects and providing recommendations for establishing minimum technical requirements for BESS GFM moving forward. | White Paper | 4507800% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% |  |  | ​Risk Mitigation
SPIDERWG MOD-031 SAR | ​SAR MOD-031-2 Ensure DER are forecasted and sent to the Regional Entity for analysis | SAR/RFI | 4509000% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | Completed | (2) Normal |  | 100% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
2023 State of Reliability Report (SOR) | ​ Rules of Procedure Section 800 states that NERC will: “conduct and report the results of an independent assessment of the overall reliability and adequacy of the interconnected North American Bulk Power Systems, both as existing and as planned” and “develop reliability performance benchmarks. The final reliability assessment reports shall be approved by the Board for publication to the electric industry and the general public” *Rules of Procedure - https://www.nerc.com/FilingsOrders/us/RuleOfProcedureDL/NERC_ROP_Effective_20190125.pdf - Section 800 | Assessment | 4509900% | Performance Analysis Subcommittee (PAS) | Completed | (2) Normal | In development stage | 100% | Changing Resource Mix | Changing Resource Mix | Performance Monitoring
BES Cyber System Information in the Cloud - project report | An overview of the processes and outcomes from a review of an entity's Microsoft Azure BCSI in the Cloud tabletop exercise | Report | 4510700% | Security Working Group (SWG) | Completed | (2) Normal | The environment and relevant security controls is complete. The results and relevant observations will comprise the report when it is published. | 100% | Cyber Vulnerabilities | Cyber - Other | ​Risk Mitigation
2022/2023 Probabilistic Assessment Scenario Case | ​evaluating and comparing Base Case probabilistic reliability indices against predetermined regional risk factors. | Assessment | 4510700% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal |  | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Improved Load Loss Measurement - Whitepaper | ​Section 1600 data request for improved load loss measurement for reliability of the BES. | Data Collection | 4510700% | Performance Analysis Subcommittee (PAS) | In Progress | (2) Normal |  | 80% | Changing Resource Mix | Changing Resource Mix | Performance Monitoring
Commissioning Technical Reference | After Review, the Commissioning Technical Reference project has been re-thought, and will now focus on specific issues that may address major issues that are resulting in misoperations. |  | 4510800% | System Protection and Control Working Group (SPCWG) | On Hold | (2) Normal | This is similar to a project being worked on by the ERO. As a result, this project is being placed on hold and the SPCWG will assist the ERO once they are ready. | 50% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
EGWG Triennial guideline review | Review 3/20 EGWG guideline on Fuel Assurance | Reliability Guideline | 4510800% | Electric Gas Working Group (EGWG) | In Progress | (2) Normal |  | 50% | Resource Adequacy and Performance | Energy Assurance | ​Risk Mitigation
8-Reliability Guideline: Recommended Approach to Interconnection Studies for BPS-Connected Inverter-Based Resources | Focused guidance on improving the study process for BPS-connected inverter-based resources, particularly with increasing penetrations of these resources and the growing complexity of performing sufficient studies to ensure BPS reliability. | Reliability Guideline | 4517000% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal | New task, on track | 50% | Inverters | Increased Penetration of Renewables | ​Risk Mitigation
2023 State of Reliability Report | ​In coordination with the PAS | Analysis | 4517000% | Event Analysis Subcommittee (EAS) | Not Started | (1) High |  | 0% |  |  | Performance Monitoring
SPIDERWG EOP-004 SAR | ​SAR EOP-004-4 Ensure the reporting of aggregate loss of DER is sent to NERC for large disturbances. | SAR/RFI | 4518100% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal |  | 50% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
C10 - White Paper: Security Risks Posed by DER and DER Aggregator | ​Follow up White Paper on the security risk posed by DER and DER aggregator. Covers both physical and cyber related impacts. | White Paper | 4518300% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | Brainstorming session complete. Initial coordination with SITES underway | 80% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
Review and Propose Metrics for EAS Reliability Guideline: Generating Unit Winter Weather Readiness | ​Review and Propose Metrics for EAS Reliability Guideline: Generating Unit Winter Weather Readiness | Reliability Guideline | 4519900% | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal | Posted for industry comment on December 14, 2022 | 80% |  |  | Performance Monitoring
Whitepaper: BES Operations in the Cloud | Breakdown concepts. Explain risks and challenges. Provide guidance and recommendations for adoption. Address cybersecurity and CIP compliance. | White Paper | 4519900% | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (1) High | Final draft completed, and submitted to September RSTC Agenda for “Request for Approval” | 99% | Cyber Vulnerabilities | Cyber Security | ​Reliability and Security Assessment
SPCWG Request for further guidance on Reliability Standard PRC-006-5 and addressing slowly declining frequency | Provide further guidance |  | 4519900% | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | Small group working on response/Subgroup SPCWG | 50% |  |  | Performance Monitoring
2023 Probabilistic Analysis Forum (PAF) | PAWG is planning the third PAF (previously 2019 and 2021) that promotes and discusses industry best practices and approaches of probabilistic-based reliability assessments | Technical Conference | 4521100% | Probabilistic Assessment Working Group (PAWG) | Not Started | (2) Normal |  | 0% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
C2-White Paper: Communication and Coordination Strategies for Transmission Entities and Distribution Entities regarding Distributed Energy Resources | Develop recommended strategies to encourage coordination between Transmission and Distribution entities on issues related to DER such as information sharing, performance requirements, DER settings, etc. | Reliability Guideline | 4526100% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (3) Low | Tabled to align with standards review (C6 activity) activity. Further, work may be duplicative with a current EPRI report. | 10% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
5- Cold Weather REC 9 - Winter Season Reserve Margin Input and Assumptions | ​​Workplan item to address Cold Weather Inquiry Report recommendation 9. RAS will use the FERC NERC RE Staff Joint Cold Weather Outage Inquiry Report findings related to winter reserve margin inputs and assumptions to inform the 2022-23 and 2023-24 NERC Winter Reliability Assessments (WRAs). Specifically, RAS, with support from the NERC Probabilistic Assessment Working Group (PAWG), will: i.enhance WRA request materials to collect information about Assessment Area inputs, assumptions, and best practices for determining anticipated resources, peak loads, managing resource and demand uncertainty, and anticipated winter reserve margins; ii.analyze assessment inputs, reported anticipated reserve margins for winter seasons, and observations from the Joint Inquiry report; and; iii.assess adequacy of resources to meet winter peak conditions and scenarios. Findings will be included in future WRAs. | Recommendations | 4526100% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Winter Reliability Assessment data request collected information from assessment areas regarding reserve margins. | 95% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Reliability and Security Assessment
6- Cold Weather REC 10 - Assess Impact of Changes to Load Shedding Plans on Seasonal Reliability | ​​Workplan item to address Cold Weather Inquiry Report recommendation 10. RAS will collect and analyze information on changes to rotating, manual load shedding plans and the potential effects these changes may have on mitigating impacts to firm load during energy emergencies within wide-area, long-duration extreme cold events. Findings will be included in future WRAs. RAS will coordinate collection and analysis with the RTOS. | Recommendations | 4526100% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Winter Reliability Assessment data request collected information from assessment areas regarding load shedding plans. | 95% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Reliability and Security Assessment
7- Cold Weather RECS 20 and 25 - Assess Information from Transfer Studies and System Studies on Reliability of Planned System | ​Workplan item to address Cold Weather Inquiry Report recommendations 20 and 25. RAS will collect information, analyze, and report on results of the following system studies performed by NERC entities that are relevant to seasonal or long-term reliability: •bi-directional seasonal transfer studies between adjacent operating entities, including identified constraints that are anticipated in extreme weather events spanning multiple RC/BA areas. (RAS will coordinate collection and analysis with the RTOS) •transfer studies identifying constraints between sub-areas or load pockets. (RAS will coordinate collection and analysis with the RTOS) •ERCOT studies to evaluate additional links between ERCOT and other interconnections in mitigating energy emergencies or improving black start capabilities | Recommendations | 4526100% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Winter Reliability Assessment data request collected information from assessment areas regarding transfers. Coordinated with the RTOS for narrative question development. Incorporated feedback from RTOS into the 2023-2024 WRA narrative. | 95% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Reliability and Security Assessment
SPIDERWG BAL-003 SAR | ​SAR BAL-003-2 Ensure consistent DER Accounting | SAR/RFI | 4526100% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal |  | 25% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
2- 2023-2024 Winter Reliability Assessment | ​Seasonal Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4526100% | Reliability Assessment Subcommittee (RAS) | Not Started | (2) Normal | Report in development. RSTC Review planned for October 18 – 30. | 0% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
SPIDERWG EOP-005 SAR | SAR EOP-005 to revise the standard to establish telemetry requirements for DERs and/or Distribution Providers (DPs). | SAR/RFI | 4527300% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal |  | 25% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
SPIDERWG PRC-006 SAR | ​SAR PRC-006-3 Clairty on imbalance equations | SAR/RFI | 4527300% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal |  | 25% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
SPIDERWG OPA/RTA SAR | ​SAR - OPA/RTA definition revision to enumerate aggregate DER | SAR/RFI | 4527300% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal |  | 5% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
1- 2023 Long-Term Reliability Assessment | ​Annual Reliability Assessment Required by NERC RoP Sect 800. | Assessment | 4527500% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Report in development. RSTC Review planned for September 26 – October 12. | 20% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
S1-Reliability Guideline: Bulk Power System Planning under Increasing Penetration of Distributed Energy Resources | Reliability Guideline providing recommended practices for performing planning studies considering the impacts of aggregate DER behavior – study approaches, analyzing BPS performance criteria incorporating DER models into studies, developing study assumptions, etc. | Reliability Guideline | 4527900% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (3) Low | On track; nearing completion of initial draft, compiling the many differing sections. Lowered priority from previous work plans with other SPIDERWG topics | 50% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
C11-White Paper: Impacts on BPS Variability, Uncertainty, and Data Collection from DER Aggregators | White paper that is tackling the planning and operational uncertainty as a follow up from the BPS Reliability Perspectives on DER Aggregators. This task is assigned to SPIDERWG.​ | White Paper | 4528000% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | In draft. | 20% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
White Paper: Modeling of DER Aggregator and DERMS Functional Impacts | White paper to explore the modeling, verification, and study impacts of a DER aggregator and DERMS functions in planning simulations.​ | White Paper | 4528000% | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | In progress. | 25% | Bulk Power System Planning | Distributed Energy Resources | ​Risk Mitigation
3- Reliability Assessment Inputs and Grid Transformation | ​Workplan item to address RISC Report recommendation 1.2 RAS will review existing long-term reliability assessment request materials to identify gaps and develop proposed narrative and/or data request items for ERO use in future LTRA beginning in 2023. Specific attention is directed to settings of controllable devices, remedial action schemes, and power electronics that stabilize the system. Development will be coordinated with necessary RSTC subgroups. | Recommendations | 4528900% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | The 2023 LTRA data request included a question in the narrative input to address this. RAS leaders discussed the request materials and the responses with SPCWG. | 50% | Bulk Power System Planning | Data and Information Requirements | ​Reliability and Security Assessment
4- Special Reliability Assessments Scope and Prioritization | ​Workplan item to address RISC Report recommendation 2.1 RAS will draft one or more project scopes for special reliability assessment(s) of extreme event impacts by geographical areas that integrate the following: (i) critical infrastructure interdependencies from water and telecom; and (ii) analytic data and insights regarding resilience. Draft project scopes will specify that the special assessments include possible mitigation plans and implementation roadmaps. Draft project scopes will be provided to the RSTC for their review, feedback, and determination of further action/assignments. | Recommendations | 4528900% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | The RAS worked with subject matter experts to develop a scope document. A draft scope is developed and the RAS recommends the RSTC assigns to a specialized task force. | 50% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Seasonal Assessment – Probabilistic Component | ​Assist RAS with incorporation of Probabilistic Enhancements to NERC Seasonal Assessments |  | 4528900% | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal |  | 100% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Collaboration Whitepaper: Privacy & Security Risks of DER Aggregators | Collaboration with SPIDERWG. Identify present architectures, technologies, threats, and risks, and controls. Provide recommendations to ensure security, reliability, and resilience. | White Paper | 4529000% | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (1) High | Final draft completed, and submitted to September RSTC Agenda for “Request for Approval” | 99% | N/A | N/A | ​Reliability and Security Assessment
PRC-019 Implementation Guidance | PRC-019 Implementation Guidance | Compliance Guidance | 4529000% | System Protection and Control Working Group (SPCWG) | Completed | (2) Normal | i. Compliance group has developed some comments and two points were addressed. Both of these were minor. Correcting a footnote and changing the title slightly to match. The larger compliance group will vote to accept this at their November meeting | 100% | Inverters | Inverter Performance | ​Risk Mitigation
PRC-024-3 Implementation Guidance | Due to changes in PRC-024-3 the Implementation Guidance will require updating to help entities demonstrate compliance with the revised standard. | Compliance Guidance | 4529100% | System Protection and Control Working Group (SPCWG) | Deferred | (2) Normal | After review, there may not be a need to revise this document as much of the -2 guidance still applies. There may be a need for a white paper for Solar/Wind cases. There is a current SAR to retire PRC-024, so group is deferring project. | 25% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
Implementation of single-phase motor models in software and testing | Work with Industry SME to develop Single Phase Motor Models Compare the model against the existing performance model to make the determination whether to proceed with dynamic phasor model in all other programs. | Research | 4529100% | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 60% | Inverters | Model Fidelity | ​Risk Mitigation
Adjustable Speed Drive (ASD) | EPRI and BPA have tested a number of ASDs. EPRI has in the past developed a model for ASD anticipated to be sufficient for large-scale simultations. EPRI is considering a more detailed model for ASD. | Research | 4529100% | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 50% | Inverters | Model Fidelity | ​Risk Mitigation
Modular implementation of the dynamic load model | ​GE PSLF and PowerWorld aready implemented dynamic load models in their software packages. PTI PSS®E will require the next release of the software - Version 35.; Testing of Modular Structure |  | 4529100% | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 70% | Inverters | Model Fidelity | ​Risk Mitigation
Events Analysis Process Document Review | ​Events Analysis Process Document Periodic Review and Update including all EAP Appendices | Program | 4529100% | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal | EAS will be requesting the RSTC to approve for industry comment posting in March 2023 | 75% |  |  | Performance Monitoring
FERC 881 discussion | Review FERC order 881 to determine if there may be impacts to PRC-023. If yes, determine what, if any action may be needed on the part of the SPCWG.​ | Assessment | 4529100% | System Protection and Control Working Group (SPCWG) | Completed | (2) Normal | This paper was accepted by the RSTC | 100% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
8- Cold Weather REC 24 - Analyze the Potential BPS Reliability Impacts of Federal and State/Provincial Entity Actions to Address Natural Gas Supply Limitations to Generators in Extreme Cold | ​Workplan item to address Cold Weather Inquiry Report recommendation 24. ​RAS will collect and analyze information for use in future LTRAs on potential BPS reliability impacts of Federal and State/Provincial entity actions to address natural gas supply limitations to generators in extreme cold conditions and/or scenarios. | Recommendations | 4529100% | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Future Long-Term Reliability Assessment data request will collect information from assessment areas regarding natural gas supply limitations. | 50% | Extreme Events | FERC-NERC Cold Weather Inquiry | ​Reliability and Security Assessment
Reliability Guideline: Methods for Establishing IROLs | Reliability Guideline: Methods for Establishing IROLs | Reliability Guideline | 4529100% | Real Time Operating Subcommittee (RTOS) | On Hold | (2) Normal | Add Metrics; place on RG Template; Post for 45 Day comment | 5% | N/A | N/A | Performance Monitoring
Review Determination of Practical Transmission Relaying Loadability Settings and Review Technical Reference Document: Transmission System Phase Backup Protections | Review the Determination of Practical Transmission Relaying Loadability Settings document and address the concers of the isue in appendix C where it says a trip can be issued instead of stating that the scheme can be unblocked, as well as do a 5 year review of it. In addition Review Technical Reference Document: Transmission System Phase Backup Protection as the second in the series of reviewing older reference material and bringing it into the three year review cycle. | White Paper | 4529100% | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal | draft created and out for review by SPCWG to ensure accuracy of the math | 75% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
16-SAR: Revisions to FAC-001 and FAC-002 | ​Enhancements to FAC-001-3 and FAC-002-2 to ensure 1) TOPs, RCs, and BAs that identify abnormal performance issues have the authority to seek corrective actions for resources not meeting their established interconnection requirements, 2) seek improvements to the requirements developed by the TO, TP, or PC (per FAC-001-3 or FAC-002-2) if gaps are identified, and 3) that those abnormal performance issues are reported to NERC for continued risk assessment. | SAR/RFI | 4529100% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% | Inverters | Inverter - Other | ​Risk Mitigation
24-White Paper: BPS-Connected IBR Commissioning Best Practices | ​White paper to highlight best practices for commissioning BPS-connected inverter-based resources to ensure appropriate protection and controls are configured and that models and studies match actual installed operational capabilities. | White Paper | 4529100% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% |  |  | ​Risk Mitigation
25-Reliability Guideline Consolidation and Updating | ​Consolidating IRPS Guidelines on IBR Performance and Improvements to Interconnection Requirements into a new guideline with plans to retire the two existing guidelines. | Reliability Guideline | 4529100% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% |  |  | ​Risk Mitigation
Develop & Publish Lessons Learned in 2023 | ​Develop & Publish Lessons Learned in 2023 Lessons Learned are developed in coordination with EAS review teams and accepted by the EAS prior to being published by NERC. | Industry Engagement | 4529100% | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal | Ongoing | 10% |  |  | Performance Monitoring
EAS Scope Document Periodic Review | ​EAS Scope Document Periodic Review | Program | 4529100% | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal |  | 20% |  |  | Performance Monitoring
Failure Modes and Mechanism Diagrams for 2023 | ​Failure Modes and Mechanism Diagrams for 2023 | Industry Engagement | 4529100% | Failure Modes and Mechanisms Task Force (FMMTF) | In Progress | (2) Normal |  | 5% |  |  | Performance Monitoring
Annual Monitoring and Situational Awareness Conference 2023 | ​ ​ Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | Conference | 4529100% | EMS Working Group (EMSWG) | Not Started | (2) Normal |  | 0% | Human Performance and Skilled Workforce | Loss of Situational Awareness | Performance Monitoring
Time Monitors | Notify RSTC of Time Monitors for 2024 and 2025 | Monitor | 4529100% | Real Time Operating Subcommittee (RTOS) | Not Started | (2) Normal | Q4 Annually | 0% |  |  | Performance Monitoring
GMD Monitors | Notify RSTC of changing GMD Monitors | Monitor | 4529100% | Real Time Operating Subcommittee (RTOS) | Not Started | (2) Normal | Q4 Annually | 0% |  |  | Performance Monitoring
Support the FERC/NERC joint inquiry recommendations on December 2022 Winter Storm Elliott as Requested | ​​Support the FERC/NERC joint inquiry recommendations on December 2022 Winter Storm Elliott as requested by the RSTC and/or Recommendation Lead Group. | Recommendations | 4529100% | Event Analysis Subcommittee (EAS) | Not Started | (2) Normal |  | 0% |  |  | Performance Monitoring
Whitepaper: AI Benefit and Risk Assessment for the BPS | ​Evaluate benefits and cybersecurity risks of AI technology use cases for industry including bulk and distribution sides. Provide recommendations for beneficial use cases, secure and reliable implementation, and mitigating controls for cyber risks. | White Paper | 4529100% | Security Integration and Technology Enablement Subcommittee (SITES) | Not Started | (2) Normal | project in pipeline for 2023 | 0% |  |  | ​Reliability and Security Assessment
Time Monitor Reference Document | Time Monitor Reference Document | Reference Document | 4529100% | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal |  | 10% |  |  | Performance Monitoring
Whitepaper: New Technology Enablement & Field Testing | Identify strategies to safely and securely trial new technology within BCS environments. Address roadblocks including compliance. | White Paper | 4532200% | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Drafting ongoing | 65% | Cyber Vulnerabilities | Cyber Security | ​Reliability and Security Assessment
Probabilistic Planning for the Tails White Paper | ​ This whitepaper will explore current approaches and practices on how ‘extreme events’ are currently considered in probabilistic planning processes and how those are assessed seasonally | White Paper | 4538000% | Probabilistic Assessment Working Group (PAWG) | In Progress | (2) Normal |  | 75% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Whitepaper on Sampling for Facility Rating programs | ​Develop a whitepaper that discusses sampling approaches for generation and transmission Facilities, and Facility Rating methodologies in association with FAC-008. Explore all aspects of the sampling processes. | White Paper | 4538000% | Facility Ratings Task Force (FRTF) | Not Started | (3) Low |  | 0% | Human Performance and Skilled Workforce | Loss of Situational Awareness | Risk Mitigation
ERAWG Work Plan #2: White Paper - Energy Reliability Assessments – Volume 2 | ​Document methods and processes for developing detailed scenarios to evaluate energy reliability that include criticalinfrastructureinterdependencies | White Paper | 4544300% | Energy Reliablity Assessment Task Force (ERATF) | In Progress | (2) Normal |  | 10% |  |  | ​Reliability and Security Assessment
Reliability Guideline on Sustaining Accurate Facility Ratings | ​Discuss the four themes identified by the ERO Enterprise as the primary issues that have impacted and posed challenges to the sustainability of accurate facility ratings, and provide guidance to registered entities to address them. | Guidance | 4545500% | Facility Ratings Task Force (FRTF) | Not Started | (2) Normal |  | 0% | Human Performance and Skilled Workforce | Loss of Situational Awareness | Risk Mitigation
Electric Vehicle (EV) Charger Model | A variety of Electric Vehicle Chargers have been tested. Lawrence Berkley National Lab (LBNL) is in the process of developing a model for EVs. | Research | 4547300% | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 20% |  |  | ​Risk Mitigation
Heat Pump Model | Deployment of dynamic data records in distribution substations and commercial buildings for purpose of load monitoring. DOE will provide resources to support data analysis | Implement | 4556500% | Load Modeling Working Group (LMWG) | In Progress | (2) Normal |  | 20% | Inverters | Model Fidelity | ​Risk Mitigation
ERATF Work Plan #3: Technical Reference document - Energy Management Plan | ​Writeatechnical referencedocument describingthe development of and considerations for seasonalextremeweatherenergymanagement plans along with rollingoperationalplanning plans that accommodate the ongoing weather forecasts and projections. | White Paper | 4556500% | Energy Reliablity Assessment Task Force (ERATF) | Not Started | (2) Normal |  | 0% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
Maintenance for Ethernet based Protection and Control Tech Reference document outline | ​With changes in technology coming, there is a need to review NERC Standards and how maintenance for Ethernet based P&C systems will fit into those standards. To that end, the SPCWG proposes developing a Technical Reference Document to provide industry guidance for impacts of systems such as 61850 architecture on NERC Protection System definition and related standards. Many utilities are incorporating these Ethernet network based P&C systems into new stations or retrofitting them into existing Protection and Control (P&C) designs. Functions traditionally done by hard wired circuits are being replaced by networking architecture, configured Ethernet messaging, merging units and high-level automated system engineering processes. Reference to include clarity in systems such as 61850 P&C designs regarding Protection System definition, relay maintenance requirements, and recommended documentation to support design. SPCWG to coordinate with team that is concurrently reviewing the definition of a Protection System, and ensure technical reference supports the outcome. This initiative also provides groundwork for future industry growth in generic-platform grid protection, monitoring, control, and management. | Reference Document | 4565700% | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal | Initial Team formed. Outline is mostly complete. Writing assignments expected at October SPCWG meeting | 20% | Increasing Complexity in Protection and Control Systems | Increasing Complexity in Protection and Control Systems | ​Risk Mitigation
ERATF Work Plan #4: Tools & Metrics - Energy Reliability Assessments | ​Developtools and metrics that are needed toperform energyreliability assessments. | Metrics | 4565700% | Energy Reliablity Assessment Task Force (ERATF) | Not Started | (2) Normal |  | 0% | Resource Adequacy and Performance | Energy Assurance | ​Reliability and Security Assessment
3-IEEE p2800 Monitoring and Support | IEEE 2800-2022 and .2 Monitoring and Support | Monitor | 4602200% | Inverter-Based Resource Performance Subcommittee (IRPS) | Not Started | (2) Normal | Ongoing, as needed. |  | N/A | N/A | ​Risk Mitigation
19-Tracking and Supporting NERC Standard Drafting Activities | IRPS will monitor and support (as needed) NERC Standard Drafting Teams related to modifications for BPS-connected inverter-based resources. Projects currently include: · Project 2021-04 Modifications to PRC-002-2 · Project 2020-02 Modifications to PRC-024 (Generator Ride-Through) · Project 2020-06 Verification of Models and Data for Generators · Project 2021-01 Modifications to MOD-025 and PRC-019 · Project 2022-04 EMT Modeling · Project 2021-02 Modification to VAR-002 · (Future Project) Updates to EOP-004 · (Future Project) IBR Performance Issues IRPS will ensure that past recommendations are addressed in NERC Standards revisions and will submit follow-on SARs if any recommendations outlined in IRPS documentation or NERC reports are not adequately addressed. | Monitor | 4602200% | Inverter-Based Resource Performance Subcommittee (IRPS) | In Progress | (2) Normal |  | 50% |  |  | ​Risk Mitigation
26-Tracking and Support for FERC Directives | ​Tracking FERC directives related to inverter-based resources and providing any support to NERC and associated activities, where applicable. |  | 4602200% | Inverter-Based Resource Performance Subcommittee (IRPS) | Not Started | (2) Normal |  | 0% | Inverters | Inverter - Other | ​Risk Mitigation