UFLS Action Plan to Re-ballot Proposed Standard

August 17th – Web-conference to discuss 1- modifications to the standard as proposed in the second ballot comments 2- discuss unresolved issues in the second ballot comments

August 18th – August 27th – 1- finalize responses to comments 2- review and revise if necessary mapping document, implementation plan, and other supporting documentation 3- double check the VSLs and Measures

August 30th – September 3rd –WECC Develops WECC Variance

September 3rd – September 10th – SDT Incorporates WECC Variance into proposed standard

September 13th – Post Webinar Materials

September 14th – Conduct Industry Webinar

September 15th – September 16th – Complete documents for posting

September 16th – Submit documents for ballot

September 20th – Meet to discuss comments on posting documents, revise documents and resubmit

September 23rd – October 2nd - Conduct 10-day ballot (third ballot)

October 7th – October 8th – Meet to discuss ballot comments, revise standard if necessary, respond to ballot comments

October 11th / October 15th /October 18th – Meet (web-conference) to finalize documents for re-ballot, if necessary

October 19th – resubmit documents for re-ballot, if necessary

October 20nd – October 31st – Conduct re-ballot, if necessary

November 3rd – NERC Board of Trustees Meeting – Present UFLS standard for approval

(Schedule on Calendar)

| August 2010 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 8 | 9 | 10 | 11 | 12 SC Grants UFLS to deviate from the process: Proceed to 10-day reballot | 13 | 14 |
| 15 | 16 | 17 * UFLS Web-conference (10 am - 12:30pm) | 18 8/18 – 8/27 Finalize responses to second ballot and revise standard accordingly | 19 | 20 | 21 |
| 8/18 – 8/27 Finalize responses to second ballot and revise standard accordingly 22 | 23 | 24 | 25 | 26 | 27 * UFLS Web-conference (10:30 am – 12:30 pm) | 28 |
| 29 | 8/30 – 9/3 WECC Develops WECC Variance 30 | 31 |  |  |  |  |

| September 2010 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| 8/30 – 9/3 WECC Develops WECC Variance |  |  | 1 | 2 | 3 | 4 |
| 9/3 – 9/10 Incorporate WECC Variance into proposed standard 5 | 6 | 7 | 8 | 9* UFLS Web-conference (1:00 – 3:30 pm) | 10 | 11 |
| 12 | 13 * POST webinar materials | 14 * Conduct UFLS Webinar | 15 | 16 * Submit Documents for Re-ballot (third ballot) | 17 | 18 |
| 19 | 20 * UFLS Web-conference -NERC comments on posting docs (1-4pm) | 21 | 22 | 9/23 – 10/2 Conduct Re-ballot of UFLS (Third Ballot) 23 | 24 | 25 |
| 9/23 – 10/2 Conduct Re-ballot of UFLS (Third Ballot) 26 | 27 | 28 | 29 | 30 |  |  |

| October 2010 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
|  |  |  |  |  | 9/23 – 10/2 Conduct Re-ballot of UFLS (Third Ballot) 1 | 2 |
| 3 | 4* Prepare and distribute ballot results/report | 5* Prepare for Baltimore meeting (breakdown of issues) | 6 | 7* UFLS Meeting Baltimore, MD | 8* UFLS Meeting Baltimore, MD | 9 |
| 10/11 – 10/18 Finalize response to ballot comments and revise standard if necessary 10 | 11 | 12 | 13 | 14 | 15* UFLS Web-conference (10:30 – 1:30) | 16 |
| 10/11 – 10/18 Finalize response to ballot comments and revise standard if necessary 17 | 18* UFLS Web-conference (10:30 -12:30pm) | 10/20 – 10/31 Conduct Re-ballot of UFLS (Fourth Ballot, if necessary) 19* Submit Documents for Re-ballot (fourth ballot, if necessary) | 20 | 21 | 22 | 23 |
| 10/20 – 10/31 Conduct Re-ballot of UFLS (Fourth Ballot, if necessary) 24 | 25 | 26 | 27 | 28 | 29 | 30 |
| 10/20 – 10/31 Conduct Re-ballot of UFLS (Fourth Ballot, if necessary) 31 |  |  |  |  |  |  |

| November 2010 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
|  | 1 | 2 | 3* NERC BOT Meeting | 4 | 5 | 6 |
| 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 |  |  |  |  |