## 2014 Work Plan
Milestone Keys:
Project Tracking Spreadsheet: 2014 Project Work Plan (Status Updated: 12/3/2014)
IC- Initial Comment |  | This worksheet displays estimates of anticipated standards development milestones for projects in 2014, and it is intended to be a project management tool for use in tracking the status of projects under development compared to their anticipated milestones. Detailed information for each project is available from their respective project pages on the NERC website. Projects that remained from 2013's Project Tracking Spreadsheet that were not prioritized in the RSDP, but that are continuing beyond the first quarter of 2014, are also represented here. Projects not anticipated to continue beyond the first quarter of 2014 are not included (information for those projects remains available under the "Standards Under Development" page on the NERC website). Note that projects listed here represent known projects for 2014. As facts and circumstances warrant, it may be necessary to update this tool, and additional projects may be added in response to regulatory directives, input from RISC, or to meet goals of the NERC strategic plan.
IB- Initial Ballot
AB - Additional Ballot
PB- Presented to BOT
F-Projected filing with FERC
FYRP- Five-year Review Posting
FYRR - Five-year Review Recommendation to SC
Project Status
No Issues with Project
Project Off Schedule by One Quarter
Project Off Schedule by Two or more Quarters |  | Projected Posting Schedule
No Development Work in Progress |  | The above is a link to the schedule of upcoming postings, which is updated weekly. It includes near term posting projections.
[14 empty] | 2014 | [17 empty] | 2015
[14 empty] | JAN | FEB |  | MAR | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Project Number | Activity/Project (Project Names Hyperlinked to Project Page) | Deliverable | Deadline, if any | Priority in 2014-2016 RSDP, if applicable (see Note 1, below) | 2013 P81 Reqs | Number of Directives | # of Guidances (see Note 2) | Directionally consistent with IERP findings | Comments | PMOS Liaison | NERC Contact | Status: Green, Yellow, Red | Milestones: Planned vs. Actual/Projected (See Notes 3 and 4) | First Quarter |  |  |  | Second Quarter | [5 empty] | Third Quarter |  |  |  |  | Fourth Quarter |  |  | First Quarter |  |  | Second Quater |  |  | Third Quarter |  |  | Fourth Quarter
2007-06 | System Protection Coordination | PRC-001, PRC-027 |  | N/A |  | 1 |  |  | A 21-day informal comment period for the preliminary draft 5 of PRC-027-1 concluded on October 21. The SDT will not respond but will consider the comments at its upcoming meetings. | Jennifer Sterling | Al McMeekin |  | Plan |  | PB
[7 empty] | 0 | Yes |  |  |  | Project extended to address an additional issue by FERC | Actual/Projected | [6 empty] | AB | [7 empty] | AB | [7 empty] | PB |  | F
2007-11 | Disturbance Monitoring | PRC-002, PRC-018 |  | Medium | 2 |  | 1 |  | Passed final ballot. | Jennifer Sterling | Steve Crutchfield |  | Plan
[7 empty] | 1 | Yes |  |  |  |  | Actual/Projected | [7 empty] | AB | [6 empty] | AB |  | PB |  | F
2007-17.3 | Protection System Maintenance: Sudden Pressure Relays | PRC-005 |  | Medium (prioritized by SC March 2014) | 1 | 1 |  |  | Passed final ballot. | Charles Yeung | Jordan Mallory |  | Plan | [14 empty] | IB |  |  |  |  | PB |  | F
[8 empty] | Yes |  |  |  |  | Actual/Projected | [5 empty] | IB | [7 empty] | AB |  |  | PB |  | F
2008-02 | Undervoltage Load Shedding and Underfrequency Load Shedding | PRC-010, PRC-022, PRC-006, PRC-004 |  | High | 2 | 1 | 1 |  | PRC-010-1 and PRC-006-2 passed final ballot. Next Step is to request authorization to post revised PRC-004 that includes UVLS. | Jennifer Sterling | Katherine Street (UVLS) and Lacey Ourso (UFLS) |  | Plan |  | IB | [10 empty] | PB |  |  | F
[7 empty] | 1 | Yes |  |  |  | Delayed to coordinate with the development of the SPS definition | Actual/Projected |  | IC | [6 empty] | IB (UVLS) | [5 empty] | IB (UFLS) |  |  |  |  | PB | F
2009-02 | Real-time Reliability Monitoring and Analysis Capabilities | New Standards or revisions to TOP and IRO standrds | January 31, 2015 deadline to address concerns in NOPR proposing to remand TOP/IRO standards | High |  | 2 |  |  | January 31, 2015 deadline to address concerns in NOPR proposing to remand TOP/IRO standards; the directives associated with this project are being addressed in Project 2014-03; consider consolidating the two projects on this spreadsheet. | Jennifer Sterling | Ed Dobrowolski |  | Plan | [7 empty] | IB | [5 empty] | AB |  |  | PB |  | F
[7 empty] | 0 | TBD |  |  |  |  | Actual/Projected | [7 empty] | IB | [5 empty] | AB |  |  | PB |  | F
2009-03 | Emergency Operations | EOP-001, EOP-002, EOP-003 being replaced by EOP-011 |  | High | 14 | 3 | 2 |  | Passed final ballot. | Gary Kruempel | Laura Anderson | Delayed to coordinate with UVLS balloting | Plan |  | IB | [10 empty] | PB |  |  | F
[7 empty] | 2 | Yes |  |  |  |  | Actual/Projected |  |  |  |  | IC | [5 empty] | IB |  |  |  | AB |  |  |  |  | PB | F
2010-02 | Connecting new facilities to the grid/Five-year Review of FAC standards | FAC-001, FAC-002 |  | Low |  | 1 | 1 |  | Passed final ballot. | Ken Goldsmith | Mallory Huggins |  | Plan |  | PB |  |  |  | IB | [6 empty] | PB |  |  | F
[7 empty] | 1 | Yes |  |  |  |  | Actual/Projected |  | PB (affirmed stds only) |  |  |  | IB | [6 empty] | PB (FAC-001 and -002) |  | F
2010-04 | Demand Data (MOD C) | MOD-016, MOD-017, MOD-018, MOD-019, MOD-020, MOD-021 |  | N/A | 10 | 10 | 4 |  | Passed final ballot. | Scott Miller | Darrel Richardson |  | Plan
[7 empty] | 4 | Yes |  |  |  |  | Actual/Projected | [6 empty] | PB |  |  |  | F
2010-05.1 | Phase 1 of Protection Systems: Misoperations | PRC-003, PRC-004 |  | N/A |  |  | 2 |  | Passed final ballot. | Jennifer Sterling | Scott Barfield |  | Plan
[7 empty] | 2 | Yes |  |  |  |  | Actual/Projected | AB | [6 empty] | AB |  |  |  |  | PB |  |  | F
2010-05.2 | Special Protection Systems: Phase 2 of Protection Systems | PRC | Self-imposed deadline for definition of SPS is February 2015 for coordination with other PRC projects. | Medium |  |  |  |  | Passed final ballot. | Jennifer Sterling | Al McMeekin |  | Plan | [8 empty] | IB | [10 empty] | PB | F | [7 empty] | PB | F
[8 empty] | Yes |  |  |  |  | Actual/Projected | [8 empty] | IB |  |  |  |  | AB | [5 empty] | PB | F | [7 empty] | PB | F
2010-13.3 | Relay Loadability Stable Power Swings | PRC | December 31, 2014 deadline to address phase 3 directives covered by this project | Medium (prioritized by SC March 2014) |  | 3 |  |  | PRC-026-1 passed an additional ballot that concluded on November 24, 2014. | Charles Long | Scott Barfield |  | Plan | [5 empty] | IB | [5 empty] | AB |  |  |  |  | PB | F
|  |  | FERC filing deadline of December 31, 2014 |  |  |  |  | n/a |  |  |  |  | Actual/Projected | [6 empty] | IB | [7 empty] | AB |  | AB (21 days) | PB | F
2010-14.1 | BARC Directives and Issues-Project 2010-14.1 Balancing Authority Reliability-based Controls | BAL-001, BAL-002, BAL-013 |  | N/A | 4 |  |  |  | BAL-002-2 did not pass additional ballot. An additional comment period and ballot will be conducted that concludes in January. | Ron Parsons | Darrel Richardson | Project extended to address an additional issue raised by FERC | Plan
[7 empty] | 0 | Yes |  |  |  |  | Actual/Projected |  | AB | [12 empty] | AB |  |  |  |  | PB | F
2010-14.2 | Phase 2 of Balancing Authority Reliability-based Control; Time Error, AGC, and Inadvertent | BAL-005-0.1b, BAL-006-2 |  | Medium | 11 | 7 | 6 |  | An informal comment period concluded on August 14, 2014. | Ken Goldsmith | Sean Cavote |  | Plan | FYRR | PB |  |  |  | IB | [6 empty] | PB |  |  | F
[7 empty] | 6 | Yes |  |  |  |  | Actual/Projected |  | FYRP |  |  | FYRR
2012-09 | Implementation of IRO Review Recommendations | IRO-003, IRO-004, IRO-008, IRO-009, IRO-010 |  | Medium | 2 | 2 |  | On hold pending | Many FYRT recommendations being addressed in Project 2014-03 | Brian Murphy | Soo Jin Kim |  | Plan | [14 empty] | IB |  |  |  |  | PB |  | F
[8 empty] | TOP/IRO project |  |  |  |  | Actual/Projected | [14 empty] | IB |  |  |  |  | PB |  | F
2012-13 | Implementation of NUC Review Recommendations | NUC-001 |  | Low |  |  |  |  | Passed final ballot. | PMOS Oversight | Stephen Eldridge |  | Plan | [5 empty] | IB | [6 empty] | PB |  |  | F
[8 empty] | Yes |  |  |  |  | Actual/Projected | [5 empty] | IB | [6 empty] | PB |  | F
2013-03 | Geomagnetic Disturbance Mitigation Stage II | TPL-007 | FERC filing deadline of January 21, 2015 | High |  | 14 |  |  | TPL-007-1 passed an additional ballot that concluded on November 21, 2014. | Brian Murphy | Mark Olson |  | Plan | [6 empty] | IB |  |  |  |  | AB |  |  |  |  | PB | F
[8 empty] | n/a |  |  |  |  | Actual/Projected | [5 empty] | IC |  |  |  | IB |  |  |  |  | AB |  | AB (25 days) | PB | F
2013-04 | VAR Directives | VAR-002 |  | N/A | 3 | 6 | 5 |  | Passed final ballot. | Ron Parsons | Soo Jin Kim |  | Plan
[7 empty] | 5 | Yes |  |  |  |  | Actual/Projected |  |  | AB |  |  |  | PB |  |  |  | F
2014-01 | Standards Applicability for Dispersed Generation Resources | Various | Goal is to complete (including regulatory approval) prior to BES Phase 2 implementation 7/1/2016 | Medium (prioritized by SC January 2014) |  |  |  |  | PRC-004-2.1a, PRC-004-3, PRC-005-2, PRC-005-3, and VAR-002-3 passed final ballot. PRC-001-1.1(X), PRC-019-2, and PRC-024-1(X) are posted for a comment period and ballot until December 19, 2014 | Gary Kruempel | Sean Cavote |  | Plan | [14 empty] | IB |  |  |  |  | PB |  | F
[8 empty] | n/a |  |  |  |  | Actual/Projected | [10 empty] | IB |  |  |  | AB |  | PB | F
2014-02 | CIP Version 5 Revisions | CIP | FERC filing deadline for certain directives of February 3, 2015. | High (prioritized by SC March 2014) |  | 8 |  |  | Standards addressing two time-sensitive directives passed final ballot. Standards incorporating four directives will be posted for an additional comment period and ballot concluding in January. | Brian Murphy | Marisa Hecht and Ryan Stewart |  | Plan | [6 empty] | IB |  |  |  |  | AB |  |  |  |  | PB |  | F
[8 empty] | n/a |  |  |  |  | Actual/Projected | [8 empty] | IB | [5 empty] | AB |  | PB |  | F
2014-03 | TOP/IRO Revisions | TOP/IRO | Deadline of January 31, 2015 | High (prioritized by SC March 2014) |  |  |  |  | 8 of 9 standards passed final ballot. Remaining standard (TOP-001-3) posted for comment and ballot concluding on January 6. | Brian Murphy | Ed Dobrowolski |  | Plan | [6 empty] | IB |  |  |  |  | AB |  |  |  |  | PB |  | F
[8 empty] | TBD |  |  |  |  | Actual/Projected | [8 empty] | IB |  |  |  | AB |  |  | AB | PB |  | F
2014-04 | Physical Security | CIP-014 | Deadline of June 5, 2014 |  |  | 7 |  |  | Passed final ballot. | Brian Murphy | Steve Crutchfield |  | Plan |  |  |  |  | IB |  | AB | PB | F
[8 empty] | n/a |  |  |  |  | Actual/Projected |  |  |  |  | IB |  |  | PB | F
TBD | TPL Directive | TPL-001 | Goal is to complete directives and file in time for FERC action prior to implementing TPL-001-4 | Medium (prioritized by SC March 2014) |  | 1 |  |  | May not move forward. | Ron Parsons | Ed Dobrowolski |  | Plan |  |  |  | IB |  |  | PB |  |  |  | F
[8 empty] | n/a |  |  |  |  | Actual/Projected |  |  |  | IB |  |  | PB |  |  |  | F
Note 1: The prioritizations here reflect those prioritizations assigned as part of the 2014-2016 Reliability Standards Development Plan (RSDP). In its approach to prioritizing Reliability Standards projects, the RSDP considered how Reliability Standard family priorities are applied to individual projects and outstanding work. Specific elements included: (1) RISC Category Rankings; (2) regulatory directives; (3) regulatory deadlines; (4) Reliability Standard requirement candidates for retirement; (5) the IERP content and quality assessments; and (6) additional considerations (fill-in-the-blank status and five-year assessment commitments). Some projects were not prioritized in the RSDP, as they were originally anticipated to be complete before the end of the first quarter of 2014, and those projects have an "N/A" designation in this column. Other projects have been added to the Project Tracking Spreadsheet that were not prioritized in the RSDP. These were added in response to regulatory directives that were issued following completion of the RSDP, and they will be prioritized according to the same process during the first quarter of 2014 according to the same process described in the RSDP. Those projects are designated as "Pending Prioritization in 1Q 2014." As discussed in the 2014-2016 RSDP, the prioritization will occur in collaboration between NERC Staff and the Standards Committee.
Note 2: Refers to guidances from regulatory orders for standards activity to consider, but that do not carry the same effect as a directive.
Note 3: In the columns at right, in some cases, an "additional ballot" is not indicated for planning purposes, but if consensus is not supported on an initial ballot, or if substantive changes occur, one will be scheduled.
Note 4: In the columns at right, there are no "plan" milestones in some cases because the project was originally planned to be complete in 2013, and the project's "actual" milestones have extended into 2014).
Note 5: In the column labeled "directionally consistent with IERP findings," directionally consistent indicates whether the Standard Drafting Team, when the project is completed, considered the recommendations from the Independent Expert Review Project and the Paragraph 81 project. After the Standard Drafting Team has considered the recommendations, the materials posted with the standards will describe the Standard Drafting Team's consideration of the findings.

## Sheet3
IB | PB | F