## non-CIP SNOPs
Filed_Date | NOC_ID | Region | Registered_Entity_Name | NCR | Reliability_Functions | Notice_of_Confirmed_Violation_or_Settlement_Agreement | Admits_OR_Agrees_and_Stipulates_OR_Neither_Admits_nor_Denies_OR_Does_Not_Contest | Total_Penalty | NERC_Violation_ID | Reliability_Standard | Requirement | Risk_Assessment | Violation_Risk_Factor | Violation_Severity_Level | Discovery_Method | Reported_to_Region_Date | Noncompliance_Start_Date | Noncompliance_End_Date | Mitigation_Expected_Completion_Date | Mitigation_Completion_Date | Date_Regional_Entity_Verified_Completion_of_Mitigation | Description_of_Noncompliance | Description_of_Risk_Assessment | Description_of_Mitigation | Other_Factors_and_Compliance_History_Discussion
2025-07-31 | NOC-2844 | SERC | Mississippi Power Company (MPC) | NCR01273 | TO | Settlement Agreement | Admits | $86,000 | 2022-00859 | FAC-008-5 | R6 | Moderate | Medium | Moderate | Self-Report | 6/3/2022 | 6/18/2007 | Present | 2026-06-30 | TBD | TBD | MPC, an affiliate of Southern Company, notified SERC that it was noncompliant with FAC-009-1 R1. MPC failed to establish Facility Ratings for a Facility consistent with the associated Facility Ratings Methodology (FRM). On October 28, 2021, SERC sent MPC an audit notification letter for an onsite audit from February 7, 2022 through February 11, 2022. The audit included FAC-008-5 R6. On January 4, 2022, while responding to the SERC Audit Data Request, MPC identified a discrepancy in the equipment listed versus that installed in the field at a 230 kV substation. At the 230 kV substation, the drawings and database indicated jumpers for the 230 kV line to switch as bundled aluminum conductor steel-reinforced cable (ACSR) jumpers rated at 2,808 amps and the most limiting element (MLE) being the ACSR conductor rated at 1,512 amps. Field verification identified one set of jumpers to actually be single all aluminum conductor (AAC) jumpers rated at 1,496 amps. While the overall change to the Facility Rating is only 16 amps or <1%, the MLE was incorrectly identified as the conductor rather than the single AAC jumpers. On January 5, 2022, MPC derated the Facility to 1,496 amps. During the SERC audit, the audit team identified two instances of incorrect element ratings that did not impact the MLE and Facility Rating. After these findings, MPC elected to conduct a walkdown of all MPC Bulk Electric System (BES) Transmission Substations using a risk-based approach. As of March 31, 2025, MPC has completed its walk-down assessment of 106 of 108 Transmission Substations, which is 98% of the MPC BES Transmission Substations. Also, in 2019, Southern Company also began a multi-year initiative to implement a single, common Transmission Facility Ratings database (TFRDB) for consistency of records, system-wide to align each of the operating companies. As part of this effort, each operating company conducted a quality assurance review (QA) of the data it would import into the new TFRDB. Overall, for the combined QA assessment and walk-downs, MPC identified 15 total instances where incorrect element ratings resulted in an incorrect MLE and incorrect Facility Ratings at eight different stations. All 15 instances resulted in a derate of the Facility Rating with derates ranging from 7% to 44%. MPC did not operate above the correct Facility Ratings. These incorrect ratings were on 115 kV and 230 kV Facilities. MPC also identified 239 instances of incorrect element ratings that did not impact the MLE and Facility Rating. These incorrect ratings were on 115 kV, 230 kV, and 500 kV Facilities. MPC has committed to complete the walkdowns by December 31, 2025, and will report all additional findings to SERC on a quarterly basis. As of March 31, 2025, the two facilities remaining to be walked down are sub-200kV facilities. The cause of the violation was inadequate controls. MPC had inadequate change management controls and legacy equipment identification controls. This noncompliance started on June 18, 2007, when FAC-009-1 R1 became enforceable on MPC and will end by December 31, 2025, when MPC completes the walkdowns and corrects all incorrect equipment and Facility Ratings. | This noncompliance posed a moderate risk and did not pose a serious or substantial risk to the reliability of the Bulk-Power System (BPS). MPC’s failure to establish Facility Ratings consistent with its FRM could result in violations of System Operating Limits, unnecessary facility trips, damage to facilities, and erroneous planning. However, the risk from the noncompliance was reduced because the incorrect Facility Ratings were limited to 15 Facilities associated with nine different Transmission Substations from the 106 of 108 Transmission Substations evaluated and the QA effort. The derate percentages ranged from 7% to 44%. MPC did not exceed the correct Facility Rating in any identified instance. The incorrect Facility Ratings were limited to the 115 kV and 230 kV systems. Also, MPC and its affiliates (collectively “Southern Company”) reviewed a year of operational data and among the discrepancies derating MLEs, nearly 80% of the affected Facilities never experienced a loading over 80% of their correct rating. Finally, fewer than 3% of the elements reviewed by Southern Company have led to discrepancies in element ratings being discovered and fewer than 0.4% of the elements reviewed resulted in modifications to the Facility Rating. No harm is known to have occurred. | To mitigate this noncompliance, MPC has or will perform the following actions: 1) re-rated transmission line in the original instance; 2) conduct walk-downs of 100% of its approximately 109 BES transmission substation facilities over a 3-year period to verify the installed FAC-008 applicable equipment that factor into the determination of Facility Ratings. Information collected during the walk-downs will be compared with information in the MPC Facility Ratings tools, and corrective actions will take place accordingly. MPC will complete the following percentages: 2023 –10% of all BES Substations 2024 –45% of all BES Substations 2025 – 45% of all BES Substations MPC will utilize a risk-based approach to prioritize station walkdowns. This approach will be based on the following criteria: (1) Substation voltage level, (2) BES stations containing medium impact cyber systems may be prioritized over stations containing low impact BES systems, and (3) stations where recent or frequent modifications have been performed (e.g., stations experiencing recent emergency restoration). Efficiency opportunities due to geographic location will also be factored into the prioritization (i.e., lower risk stations located near higher risk stations); 3) communicated to Senior Management the importance of FAC-008 walkdowns and ensuring that the appropriate resources are in place for success; 4) appointed a Project Manager to manage/implement substation walkdowns; 5) developed a comprehensive listing of all BES transmission substations to be included in FAC-008 walkdowns; 6) updated current change management procedure to ensure that changes made in the field are accurately reflected in drawings and databases. - Updates to Facility Rating drawings and databases will involve verification controls, such as the addition of peer checks, managed in a new Facility Ratings Change Tool (FRCT). - Engineering, field, and control center verification will be required prior to energizing new equipment. Processes will be developed for both scheduled and emergency work. - Added Swimlane charts that describes roles and tools utilized in the Facility Ratings Change Management Process; 7) evaluated, determined, and procured resources and equipment needed to identify equipment in the field such as conductor sizes. MPC utilizes experienced substation and Operations personnel for the physical walkdowns of the stations. MPC personnel also utilize high-definition cameras and drones, as needed, to verify equipment in the field. Other tools may be employed, as needed, to verify accuracy; 8) provided initial Inspection Training to personnel performing and supporting physical substation walkdowns; 9) developed a Southern Company Transmission Facility Ratings Database (TFRDB) to maintain equipment facility ratings consistently across Operating Companies to maintain equipment facility ratings (replaces existing spreadsheet process). This will include all equipment, including Bushing Mounted Current Transformers (BCTs). The following controls are intended to reasonably prevent reoccurrence: - Consolidated databases to utilize modern program logic and not rely upon outdated databases - Implemented capabilities to execute “change report” queries - Associated ratings with common equipment to reduce human “keying errors”; 10) trained employees impacted and responsible for performing tasks associated with TSO-14, Mississippi Power Facility Ratings on the updates made to improve the process; 11) create Facility Rating Diagrams for BES Substations. Upon completion, MPC will have an entire set of diagrams, which show all BES substation equipment evaluated in the Facility Rating process. Controls will be established to ensure the diagrams will be maintained to accurately reflect field conditions; 12) complete the Substation Facility Walkdown project and will correct all facility rating discrepancies identified. MPC will continue to provide quarterly status reports to SERC. The reports will include a status update of the total number of completed substation walkdowns and identify all findings. The reports will be provided within 30 days after the end of each calendar quarter; and 13) implemented quarterly reporting of Facility Rating substation walkdowns to committee of senior leadership. This committee is tasked with program oversight of NERC Operations and Planning Standards to ensure business accountability. Reports outline the status/progress of Southern Company FAC-008 Facility Rating substation walkdown baseline program throughout the completion of the project. | SERC determined that MPC’s FAC-008-5 R6 compliance history should not serve as a basis for aggravating the penalty because while the prior noncompliances of MPC’s Southern Company affiliates were arguably similar, the prior noncompliances arose from different causes and the mitigation activities of the prior noncompliance would not have prevented the current MPC instance. Specifically, the most recent prior noncompliance involved conductors, and mitigation would not have prevented the current violation. SERC is awarding penalty credit to MPC due to four separate factors. First, SERC is awarding penalty credit for MPC’s cooperation throughout the enforcement process relating to the Alleged Violation. MPC voluntarily provided SERC with information that was timely, detailed, thoughtful, organized, and thorough. MPC fully cooperated in SERC’s investigation of the Alleged Violation and all associated mitigating activities and openly shared information regarding its processes, procedures, internal controls, assets, systems, and organization. Second, SERC is awarding penalty credit for MPC’s internal compliance program (ICP). SERC recognizes and values MPC’s continuous commitment to improving its internal compliance program (ICP) and the resources it is expending on its comprehensive walk-downs. MPC has also committed to establishing a risk-based walk-down control which will utilize an annual sampling of Facilities to provide assurance of program controls implemented during the baseline walkdowns. Third, SERC is awarding penalty credit because MPC agreed to settle the Alleged Violation, which avoids a hearing. A willingness to resolve cases without the need for a trial-type hearing reduces the amount of time and resources that SERC, NERC, and the Commission would otherwise expend to resolve the Alleged Violation. Additionally, it is important to promote prompt resolution of enforcement actions so that MPC can focus on mitigation and reducing risks to reliability. Fourth, SERC is awarding penalty credit because MPC recognized and affirmatively accepted responsibility for its conduct by admitting to the Alleged Violation. There is independent value in MPC accepting responsibility for its violations.